## Tables
DOCUMENT SUBMISSION STATUS
DOCUMENT TYPE | Code 1 | Code 2 | Code 3 | AR (ATJV) | UR (ATJV) | UR (DAR) | TOTAL DOCS | TOTAL SUBMITTED | TOTAL PENDING
ICD | [6 empty] | 3 | 0 | 3
ITP | 1 |  |  |  |  | 11 | 19 | 12 | 7
MST |  | 1 |  | 8 | 1 | 2 | 19 | 12 | 7
MTS | 10 | 6 |  | 4 |  | 3 | 28 | 23 | 5
OMM | [6 empty] | 3 | 0 | 3
OTM | [6 empty] | 3 | 0 | 3
PQ | 4 | 2 | 1 | 4 |  |  | 11 | 11
SDD | [6 empty] | 3 | 0 | 3
TCD | [6 empty] | 3 | 0 | 3
Warranty | [6 empty] | 3 | 0 | 3
Grand Total | 15 | 9 | 1 | 16 | 1 | 16 | 95 | 58 | 37
DOCUMENT SUBMISSION BY VENDOR
VENDOR | Code 1 | Code 2 | Code 3 | AR (ATJV) | UR (ATJV) | UR (DAR) | TOTAL DOCS | TOTAL SUBMITTED | TOTAL PENDING
ANIXTER |  | 3 |  | 6 | 1 | 4 | 14 | 14 | 0
DELL | [6 empty] | 1 | 0 | 1
GENETIC |  | 1 |  |  |  |  | 3 | 1 | 2
HONEYWELL | 1 |  |  | 1 |  |  | 3 | 2 | 1
HP | [5 empty] | 1 | 9 | 1 | 8
HUAWEI |  |  |  | 1 |  |  | 1 | 1 | 0
IDEX |  |  |  | 1 |  |  | 4 | 1 | 3
LEGRAND |  |  |  | 2 |  | 1 | 3 | 3 | 0
METRA | 10 | 1 |  |  |  |  | 13 | 11 | 2
NAFFCO |  |  | 1 |  |  |  | 1 | 1 | 0
SAFELINE |  | 1 |  | 3 |  | 3 | 7 | 7 | 0
SAPLING | 1 |  |  | 1 |  | 1 | 3 | 3 | 0
SETRA | 1 | 1 |  | 1 |  | 1 | 4 | 4 | 0
SITA | 1 | 1 |  |  |  |  | 16 | 2 | 14
SONIC ELECTRONICS |  | 1 |  |  |  | 2 | 9 | 3 | 6
TECHNACY | [5 empty] | 3 | 3 | 3 | 0
(blank) | 1 | [5 empty] | 1 | 1 | 0
Grand Total | 9 | 1 | 16 | 1 | 1 | 16 | 95 | 58 | 37

## T_DocLog
SN | Column3 | DOCTYPE | DOCR | DISC | Column2 | DOC_SUB | Vender Name | System | Action | SD_C | REV_C | ST_C | JV_LRR | JCD_C | STATUS_C | REVIEW_C | REVIEW_C2 | ST0 | STD0 | STD02 | STD03 | JVT0 | JVD0 | STATUS0 | REVIEW0 | ST1 | STD1 | STD12 | STD13 | JVT1 | JVD1 | STATUS1 | REVIEW1 | ST2 | ST22 | ST23 | STD2 | JVT2 | JVD2 | STATUS2 | REVIEW2 | ST3 | STD3 | JVT3 | JVD3 | STATUS3 | REVIEW3 | ST4 | STD4 | JVT4 | JVD4 | STATUS4 | REVIEW5 | ST5 | STD5 | JVT5 | JVD5 | STATUS5 | REVIEW52 | REMARKS
1 |  | PQ | --- | General | Project Submittal | Prequalification of Distributor (PQM) - Metra Cisco Partner | METRA | CNE |  | ATLS-004-PQM-ICT-00001-R01 | 1 | 2025-05-08 | ATV-1300000403-PQM-ICT-00005-R01 | 2025-05-12 | Code 1 | 4 | 4 | ATLS-004-PQM-ICT-00001-R00 | 2025-04-10 | ATV-1300000403-PQM-ICT-00005-R00 | 2025-04-13 | ATV-1300000403-PQM-ICT-00005 | 2025-04-13 | Code 2 |  | ATLS-004-PQM-ICT-00001-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00005-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00005-R01 | 2025-05-12 | Code 1
2 |  | PQ | --- | General | Project Submittal | Prequalification of Distributor (PQM) - Anixter CommScope Partner | ANIXTER | SCN |  | ATLS-004-PQM-ICT-00002-R01 | 1 | 2025-05-08 | ATV-1300000403-PQM-ICT-00006-R01 | 2025-05-12 | Code 2 | 4 | 4 | ATLS-004-PQM-ICT-00002-R00 | 2025-04-10 | ATV-1300000403-PQM-ICT-00006-R00 | 2025-04-13 | ATV-1300000403-PQM-ICT-00006 | 2025-04-13 | Code 2 |  | ATLS-004-PQM-ICT-00002-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00006-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00006-R01 | 2025-05-12 | Code 2
3 |  | PQ | --- | General | Project Submittal | Prequalification of Distributor (PQM) - SITA | SITA | BCE, IDS, BRS |  | ATLS-004-PQM-ICT-00003-R01 | 1 | 2025-04-28 | ATV-1300000403-PQM-ICT-00004-r01 | 2025-04-30 | Code 1 | 2 | 2 | ATLS-004-PQM-ICT-00003-R00 | 2025-04-10 | ATV-1300000403-PQM-ICT-00004-R00 | 2025-04-12 | ATV-1300000403-PQM-ICT-00004 | 2025-04-13 | Code 2 |  | ATLS-004-PQM-ICT-00003-R01 | 2025-04-28 | ATV-1300000403-PQM-ICT-00004-R01 | 2025-04-28 | ATV-1300000403-PQM-ICT-00004-r01 | 2025-04-30 | Code 1
4 |  | PQ | --- | General | Project Submittal | Prequalification For IDEX Services Co. | IDEX | CPGS |  | ATLS-004-PQM-ICT-00004-R01 | 1 | 2025-05-01 | ATV-1300000403-PQM-ICT-00007 | 2025-04-30 | AR (ATJV) | 39 | 39 | ATLS-004-PQM-ICT-00004-R00 | 2025-04-17 | ATV-1300000403-PQM-ICT-00007-R00 | 2025-04-17 | ATV-1300000403-PQM-ICT-00007 | 2025-04-30 | Code 3 |  | ATLS-004-PQM-ICT-00004-R01 | 2025-05-01 | ATV-1300000403-PQM-ICT-00007-R01 |  |  |  | AR (ATJV)
5 |  | PQ | --- | General | Project Submittal | Prequalification For Saudi Electronic Trading and Contracting Company Limited (SETRA) | SETRA | SACS |  | ATLS-004-PQM-ICT-00005-R02 | 2 | 2025-05-20 | ATV-1300000403-PQM-ICT-00008-R02 | 2025-05-26 | Code 1 | 6 | 6 | ATLS-004-PQM-ICT-00005-R00 | 2025-04-18 | ATV-1300000403-PQM-ICT-00008-R00 | 2025-04-20 | ATV-1300000403-PQM-ICT-00008 | 2025-04-27 | Code 2 |  | ATLS-004-PQM-ICT-00005-R01 | 2025-05-07 | ATV-1300000403-PQM-ICT-00008-R01 | 2025-05-08 | ATV-1300000403-PQM-ICT-00008-R01 | 2025-05-11 | Code 2 |  | ATLS-004-PQM-ICT-00005-R02 | 2025-05-19 | ATV-1300000403-PQM-ICT-00008-R02 | 2025-05-20 | ATV-1300000403-PQM-ICT-00008-R02 | 2025-05-26 | Code 1
6 |  | PQ | --- | General | Project Submittal | Prequalification of Subcontractor for ICT Works - Atlas Security |  |  |  | ATLS-004-PAS-ICT-00002-R00 | 0 | 2025-02-03 | ATV-1300000403-PAS-ICT-00002 | 2025-04-06 | Code 1 | 62 | 62 | ATLS-004-PAS-ICT-00002-R00 | 2025-02-03 | ATV-1300000403-PAS-ICT-00002-R00 | 2025-03-27 | ATV-1300000403-PAS-ICT-00002 | 2025-04-06 | Code 1
7 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Structured Cabling Network - Backbone cabling | ANIXTER | SCN |  | ATLS-004-MTS-ICT-00020-R01 | 1 | 2025-06-04 | ATV-1300000403-MTS-ICT-00002-R00 | 2025-04-22 | AR (ATJV) | 5 | 5 | ATLS-004-MTS-ICT-00020-R00 | 2025-04-18 | ATV-1300000403-MTS-ICT-00002-R00 | 2025-04-19 | ATV-1300000403-MTS-ICT-00002-R00 | 2025-04-22 | Code 2 |  | ATLS-004-MTS-ICT-00020-R01 | 2025-06-04 | ATV-1300000403-MTS-ICT-00002-R01 |  |  |  | AR (ATJV)
8 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Stuctured Cabling Network - Horizontal cabling | ANIXTER | SCN |  | ATLS-004-MTS-ICT-00019-R01 | 1 | 2025-06-04 | ATV-1300000403-MTS-ICT-00001-R00 | 2025-04-22 | AR (ATJV) | 5 | 5 | ATLS-004-MTS-ICT-00019-R00 | 2025-04-17 | ATV-1300000403-MTS-ICT-00001-R00 | 2025-04-19 | ATV-1300000403-MTS-ICT-00001-R00 | 2025-04-22 | Code 2 |  | ATLS-004-MTS-ICT-00019-R01 | 2025-06-04 | ATV-1300000403-MTS-ICT-00001-R01 |  |  |  | AR (ATJV)
9 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Airport Area Network - AAN | METRA | CNE |  | ATLS-004-MTS-ICT-00009-R00 | 0 | 2025-05-06 | ATV-1300000403-MTS-ICT-00017-R00 | 2025-05-19 | Code 2 | 13 | 13 | ATLS-004-MTS-ICT-00009-R00 | 2025-05-06 | ATV-1300000403-MTS-ICT-00017-R00 | 2025-05-06 | ATV-1300000403-MTS-ICT-00017-R00 | 2025-05-19 | Code 2
10 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - CCTV Dedicate Network | METRA | CNE |  | ATLS-004-MTS-ICT-00010-R01 | 1 | 2025-05-13 | ATV-1300000403-MTS-ICT-00005-R01 | 2025-05-14 | Code 1 | 1 | 1 | ATLS-004-MTS-ICT-00010-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00005-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00005-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00010-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00005-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00005-R01 | 2025-05-14 | Code 1
11 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - RSAF Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00018-R01 | 1 | 2025-05-19 | ATV-1300000403-MTS-ICT-00012-R01 | 2025-05-21 | Code 1 | 2 | 2 | ATLS-004-MTS-ICT-00018-R00 | 2025-04-25 | ATV-1300000403-MTS-ICT-00012-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00012-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00018-R01 | 2025-05-19 | ATV-1300000403-MTS-ICT-00012-R01 | 2025-05-20 | ATV-1300000403-MTS-ICT-00012-R01 | 2025-05-21 | Code 1
12 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - GID Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00013-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00008-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00013-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00008-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00008-R00 | 2025-04-30 | Code 2 |  | ATLS-004-MTS-ICT-00013-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00008-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00008-R01 | 2025-05-26 | Code 1
13 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - NIC Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00015-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00010-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00015-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00010-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00010-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00015-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00010-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00010-R01 | 2025-05-26 | Code 1
14 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - GDP Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00012-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00007-R01 | 2025-05-25 | Code 1 | 2 | 2 | ATLS-004-MTS-ICT-00012-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00007-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00007-R00 | 2025-04-30 | Code 2 |  | ATLS-004-MTS-ICT-00012-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00007-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00007-R01 | 2025-05-25 | Code 1
15 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Customs Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00011-R01 | 1 | 2025-05-27 | ATV-1300000403-MTS-LAN-00006-R01 | 2025-05-31 | Code 1 | 4 | 4 | ATLS-004-MTS-ICT-00011-R00 | 2025-04-24 | ATV-1300000403-MTS-LAN-00006-R00 | 2025-04-26 | ATV-1300000403-MTS-LAN-00006-R00 | 2025-05-01 | Code 2 |  | ATLS-004-MTS-ICT-00011-R01 | 2025-05-27 | ATV-1300000403-MTS-LAN-00006-R01 | 2025-05-29 | ATV-1300000403-MTS-LAN-00006-R01 | 2025-05-31 | Code 1
16 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Public Area Network | METRA | CNE |  | ATLS-004-MTS-ICT-00016-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-LAN-00013-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00016-R00 | 2025-04-28 | ATV-1300000403-MTS-LAN-00013-R00 | 2025-04-29 | ATV-1300000403-MTS-LAN-00013-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00016-R01 | 2025-05-23 | ATV-1300000403-MTS-LAN-00013-R01 | 2025-05-24 | ATV-1300000403-MTS-LAN-00013-R01 | 2025-05-26 | Code 1
17 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - Intelligent Service Network | METRA | CNE |  | ATLS-004-MTS-ICT-00014-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00009-R01 | 2025-05-26 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00014-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00009-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00009-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00014-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00009-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00009-R01 | 2025-05-26 | Code 1
18 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Active Network Equipment - RFID Dedicated Network | METRA | CNE |  | ATLS-004-MTS-ICT-00017-R01 | 1 | 2025-05-23 | ATV-1300000403-MTS-ICT-00011-R01 | 2025-05-25 | Code 1 | 2 | 2 | ATLS-004-MTS-ICT-00017-R00 | 2025-04-25 | ATV-1300000403-MTS-ICT-00011-R00 | 2025-04-26 | ATV-1300000403-MTS-ICT-00011-R00 | 2025-05-03 | Code 2 |  | ATLS-004-MTS-ICT-00017-R01 | 2025-05-23 | ATV-1300000403-MTS-ICT-00011-R01 | 2025-05-24 | ATV-1300000403-MTS-ICT-00011-R01 | 2025-05-25 | Code 1
19 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Master Clock System | SAPLING | MCS |  | ATLS-004-MTS-ICT-00002-R01 | 1 | 2025-05-10 | ATV-1300000403-MTS-ICT-00003-R01 | 2025-05-13 | Code 1 | 3 | 3 | ATLS-004-MTS-ICT-00002-R00 | 2025-04-23 | ATV-1300000403-MTS-ICT-00003-R00 | 2025-04-23 | ATV-1300000403-MTS-ICT-00003-R00 | 2025-04-29 | Code 2 |  | ATLS-004-MTS-ICT-00002-R01 | 2025-05-10 | ATV-1300000403-MTS-ICT-00003-R01 | 2025-05-10 | ATV-1300000403-MTS-ICT-00003-R01 | 2025-05-13 | Code 1
20 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Internet Protocol Television System | TECHNACY | IPTV |  | ATLS-004-MTS-ICT-00004-R01 | 1 | 2025-05-28 | ATV-1300000403-MTS-ICT-00015-R00 | 2025-05-19 | UR (DAR) | 12 | 12 | ATLS-004-MTS-ICT-00004-R00 | 2025-04-30 | ATV-1300000403-MTS-ICT-00015-R00 | 2025-05-01 | ATV-1300000403-MTS-ICT-00015-R00 | 2025-05-19 | Code 2 |  | ATLS-004-MTS-ICT-00004-R01 | 2025-05-28 | ATV-1300000403-MTS-ICT-00015-R01 | 2025-06-04 |  |  | UR (DAR)
21 |  | MTS | --- | Communications | Project Submittal | Material Submittal for IP Based Intercom System | GENETIC | VIS |  | ATLS-004-MTS-ICT-00026-R00 | 0 | 2025-05-30 | ATV-1300000403-MTS-ICT-00023-R00 | 2025-06-03 | Code 2 | 4 | 4 | ATLS-004-MTS-ICT-00026-R00 | 2025-05-30 | ATV-1300000403-MTS-ICT-00023-R00 | 2025-05-31 | ATV-1300000403-MTS-ICT-00023-R00 | 2025-06-03 | Code 2
22 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Public Address System | SONIC ELECTRONICS | PAS |  | ATLS-004-MTS-ICT-00007-R00 | 0 | 2025-05-05 | ATV-1300000403-MTS-ICT-00016-R00 | 2025-05-07 | Code 2 | 2 | 2 | ATLS-004-MTS-ICT-00007-R00 | 2025-05-05 | ATV-1300000403-MTS-ICT-00016-R00 | 2025-05-05 | ATV-1300000403-MTS-ICT-00016-R00 | 2025-05-07 | Code 2
23 |  | MTS | --- | Security and Safety | Project Submittal | Material Submittal for Security Access Control System | SETRA | SACS |  | ATLS-004-MTS-ICT-00003-R00 | 0 | 2025-04-29 | ATV-1300000403-MTS-ICT-00014-R00 | 2025-05-15 | Code 2 | 16 | 16 | ATLS-004-MTS-ICT-00003-R00 | 2025-04-29 | ATV-1300000403-MTS-ICT-00014-R00 | 2025-04-30 | ATV-1300000403-MTS-ICT-00014-R00 | 2025-05-15 | Code 2
24 |  | MTS | --- | Security and Safety | Project Submittal | Material Submittal for Fire Alarm System | HONEYWELL | FAS |  | --- |  |  |  |  | --- | --- | ---
25 |  | MTS | --- | Security and Safety | Project Submittal | Material Submittal for Closed Circuit Television System | ANIXTER | CCTV |  | ATLS-004-MTS-ICT-00001-R03 | 3 | 2025-06-04 | ATV-1300000403-MTS-ICT-00004-R02 | 2025-05-26 | AR (ATJV) | 5 | 5 | ATLS-004-MTS-ICT-00001-R00 | 2025-04-23 | ATV-1300000403-MTS-ICT-00004-R00 | 2025-04-24 | ATV-1300000403-MTS-ICT-00004-R00 | 2025-04-29 | Code 2 |  | ATLS-004-MTS-ICT-00001-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00004-R01 | 2025-05-13 | ATV-1300000403-MTS-ICT-00004-R01 | 2025-05-15 | Code 2 |  | ATLS-004-MTS-ICT-00001-R02 | 2025-05-21 | ATV-1300000403-MTS-ICT-00004-R02 | 2025-05-21 | ATV-1300000403-MTS-ICT-00004-R02 | 2025-05-26 | Code 1 |  | ATLS-004-MTS-ICT-00001-R03 | 2025-06-04 |  |  | AR (ATJV)
26 |  | MTS | --- | Security and Safety | Project Submittal | Material Submittal for Car Park Guidance System | IDEX | CPGS |  | --- |  |  |  |  | --- | --- | ---
27 |  | MTS | --- | Special Airport Systems | Project Submittal | Material Submittal for Border Control Systems | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
28 |  | MTS | --- | Special Airport Systems | Project Submittal | Material Submittal for Information Display Systems | SITA | IDS |  | --- |  |  |  |  | --- | --- | ---
29 |  | MTS | --- | Special Airport Systems | Project Submittal | Material Submittal for Baggage Reonciliation System | SITA | BRS |  | ATLS-004-MTS-ICT-00022-R00 | 0 | 2025-05-15 | ATV-1300000403-MTS-ICT-00018-R00 | 2025-05-20 | Code 2 | 5 | 5 | ATLS-004-MTS-ICT-00022-R00 | 2025-05-15 | ATV-1300000403-MTS-ICT-00018-R00 | 2025-05-18 | ATV-1300000403-MTS-ICT-00018-R00 | 2025-05-20 | Code 2
30 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of Stuctured Cabling Network - Backbone cabling | ANIXTER | SCN | Shahul / Ibrar | ATLS-004-MST-ICT-00006-R00 | 0 | 2025-05-29 |  |  | AR (ATJV) | 11 | 11 | ATLS-004-MST-ICT-00006-R00 | 2025-05-29 |  |  |  |  | AR (ATJV)
31 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of Stuctured Cabling Network - Horizontal cabling | ANIXTER | SCN | Shahul / Ibrar | ATLS-004-MST-ICT-00004-R00 | 0 | 2025-05-25 |  |  | AR (ATJV) | 15 | 15 | ATLS-004-MST-ICT-00004-R00 | 2025-05-25 |  |  |  |  | AR (ATJV)
32 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of Active Network Equipment - AAN, CCTV Dedicate Network, RSAF Dedicated Network, GID, NIC,GDP, Customs. Pubic Area Network, Intelligent Service, VOIP, Corporate, Public | METRA | CNE | Jideh | --- |  |  |  |  | --- | --- | ---
33 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of Master Clock System | SAPLING | MCS | Cahit | ATLS-004-MST-ICT-00011-R00 | 0 | 2025-05-29 |  |  | AR (ATJV) | 11 | 11 | ATLS-004-MST-ICT-00011-R00 | 2025-05-29 |  |  |  |  | AR (ATJV)
34 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of Internet Protocol Television System | TECHNACY | IPTV | Cahit | ATLS-004-MST-ICT-00008-R00 | 0 | 2025-05-31 |  |  | UR (DAR) | 9 | 9 | ATLS-004-MST-ICT-00008-R00 | 2025-05-31 | ATV-1300000403-MST-ICT-00002-R00 | 2025-06-03 |  |  | UR (DAR)
35 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of IP Based Intercom System | GENETIC | VIS | Cahit | --- |  |  |  |  | --- | --- | ---
36 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS | Likhil | ATLS-004-MST-ICT-00010-R00 | 0 | 2025-06-03 |  |  | UR (DAR) | 6 | 6 | ATLS-004-MST-ICT-00010-R00 | 2025-06-03 | ATV-1300000403-MST-ICT-00003-R00 | 2025-06-04 |  |  | UR (DAR)
37 |  | MST | --- | Security and Safety | Project Submittal | Method Statement for the installation of Access Control System | SETRA | SACS | Sahla | ATLS-004-MST-ICT-00007-R00 | 0 | 2025-05-25 |  |  | AR (ATJV) | 15 | 15 | ATLS-004-MST-ICT-00007-R00 | 2025-05-25 |  |  |  |  | AR (ATJV)
38 |  | MST | --- | Security and Safety | Project Submittal | Method Statement for the installation of Fire Alarm System | HONEYWELL | FAS | Riswan | ATLS-004-MST-ICT-00009-R00 | 0 | 2025-05-26 |  |  | AR (ATJV) | 14 | 14 | ATLS-004-MST-ICT-00009-R00 | 2025-05-26 |  |  |  |  | AR (ATJV)
39 |  | MST | --- | Security and Safety | Project Submittal | Method Statement for the installation of Closed Circuit Television System | ANIXTER | CCTV | Cahit | ATLS-004-MST-ICT-00005-R00 | 0 | 2025-05-31 |  |  | UR (ATJV) | 9 | 9 | ATLS-004-MST-ICT-00005-R00 | 2025-05-31 |  |  |  |  | UR (ATJV)
40 |  | MST | --- | Security and Safety | Project Submittal | Method Statement for the installation of Car Park Guidance System | IDEX | CPGS | Sahla | --- |  |  |  |  | --- | --- | ---
41 |  | MST | --- | Special Airport Systems | Project Submittal | Method Statement for the installation of Border Control Systems | SITA | BCE | Likhil | --- |  |  |  |  | --- | --- | ---
42 |  | MST | --- | Special Airport Systems | Project Submittal | Method Statement for the installation of Information Display Systems | SITA | IDS | Cahit | --- |  |  |  |  | --- | --- | ---
43 |  | MST | --- | Special Airport Systems | Project Submittal | Method Statement for the installation of Baggage Reonciliation System | SITA | BRS | Sahla | --- |  |  |  |  | --- | --- | ---
44 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of Stuctured Cabling Network - Backbone cabling | ANIXTER | SCN |  | ATLS-004-ITP-ICT-00006-R00 | 0 | 2025-05-20 |  |  | UR (DAR) | 20 | 20 | ATLS-004-ITP-ICT-00006-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00007-R00 | 2025-05-29 |  |  | UR (DAR)
45 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of Stuctured Cabling Network - Horizontal cabling | ANIXTER | SCN |  | ATLS-004-ITP-ICT-00002-R00 | 0 | 2025-05-20 |  |  | UR (DAR) | 20 | 20 | ATLS-004-ITP-ICT-00002-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00006-R00 | 2025-05-29 |  |  | UR (DAR)
46 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of Active Network Equipment - Airport Area Network - AAN | METRA | CNE |  | --- |  |  |  |  | --- | --- | ---
47 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of Master Clock System | SAPLING | MCS |  | ATLS-004-ITP-ICT-00007-R00 | 0 | 2025-05-21 |  |  | UR (DAR) | 19 | 19 | ATLS-004-ITP-ICT-00007-R00 | 2025-05-21 | ATV-1300000403-ITP-ICT-00005-R00 | 2025-05-29 |  |  | UR (DAR)
48 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of Internet Protocol Television System | TECHNACY | IPTV |  | ATLS-004-ITP-ICT-00008-R00 | 0 | 2025-05-21 |  |  | UR (DAR) | 19 | 19 | ATLS-004-ITP-ICT-00008-R00 | 2025-05-21 | ATV-1300000403-ITP-ICT-00011-R00 | 2025-05-31 |  |  | UR (DAR)
49 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of IP Based Intercom System | GENETIC | VIS |  | --- |  |  |  |  | --- | --- | ---
50 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | ATLS-004-ITP-ICT-00012-R00 | 0 | 2025-05-30 |  |  | UR (DAR) | 10 | 10 | ATLS-004-ITP-ICT-00012-R00 | 2025-05-30 | ATV-1300000403-ITP-ICT-00010-R00 | 2025-05-31 |  |  | UR (DAR)
51 |  | ITP | --- | Security and Safety | Project Submittal | ITP for the installation of Access Control System | SETRA | SACS |  | ATLS-004-ITP-ICT-00009-R00 | 0 | 2025-05-23 |  |  | UR (DAR) | 17 | 17 | ATLS-004-ITP-ICT-00009-R00 | 2025-05-23 | ATV-1300000403-ITP-ICT-00008-R00 | 2025-05-29 |  |  | UR (DAR)
52 |  | ITP | --- | Security and Safety | Project Submittal | ITP for the installation of Fire Alarm System | HONEYWELL | FAS |  | ATLS-004-ITP-ICT-00011-R01 | 1 | 2025-05-23 |  |  | Code 1 | 17 | 17 | ATLS-004-ITP-ICT-00011-R00 | 2025-05-23 | ATV-1300000403-ITP-ICT-00002-R00 | 2025-04-26 |  |  | Code 2 |  | ATLS-004-ITP-ICT-00011-R01 |  | ATV-1300000403-ITP-ICT-00001-R01 |  |  |  | Code 1
53 |  | ITP | --- | Security and Safety | Project Submittal | ITP for the installation of Closed Circuit Television System | ANIXTER | CCTV |  | ATLS-004-ITP-ICT-00005-R00 | 0 | 2025-05-21 |  |  | UR (DAR) | 19 | 19 | ATLS-004-ITP-ICT-00005-R00 | 2025-05-21 | ATV-1300000403-ITP-ICT-00013-R00 | 2025-05-31 |  |  | UR (DAR)
54 |  | ITP | --- | Security and Safety | Project Submittal | ITP for the installation of Car Park Guidance System | IDEX | CPGS |  | --- |  |  |  |  | --- | --- | ---
55 |  | ITP | --- | Special Airport Systems | Project Submittal | ITP for the installation of Border Control Systems | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
56 |  | ITP | --- | Special Airport Systems | Project Submittal | ITP for the installation of Information Display Systems | SITA | IDS |  | --- |  |  |  |  | --- | --- | ---
57 |  | ITP | --- | Special Airport Systems | Project Submittal | ITP for the installation of Baggage Reonciliation System | SITA | BRS |  | --- |  |  |  |  | --- | --- | ---
58 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Data Communication Hardware - CCTV and Other Applications | DELL | DCH |  | --- |  |  |  |  | --- | --- | ---
59 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | ATLS-004-MTS-ICT-00023-R00 | 0 | 2025-05-31 |  |  | UR (DAR) | 9 | 9 | ATLS-004-MTS-ICT-00023-R00 | 2025-05-31 | ATV-1300000403-MTS-ICT-00025-R00 | 2025-06-03 |  |  | UR (DAR)
60 |  | MST | --- | Communications | Project Submittal | Method Statement for the installation of Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS | Likhil | --- |  |  |  |  | --- | --- | ---
61 |  | SDD | --- | Communications | Project Submittal | System Design Document for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
62 |  | SDD | --- | Communications | Project Submittal | System Design Document for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
63 |  | SDD | --- | Communications | Project Submittal | System Design Document for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
64 |  | ICD | --- | Communications | Project Submittal | Interface Control Document for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
65 |  | ICD | --- | Communications | Project Submittal | Interface Control Document for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
66 |  | ICD | --- | Communications | Project Submittal | Interface Control Document for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
67 |  | TCD | --- | Communications | Project Submittal | Testing and Commissioning Document Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
68 |  | TCD | --- | Communications | Project Submittal | Testing and Commissioning Document Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
69 |  | TCD | --- | Communications | Project Submittal | Testing and Commissioning Document Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
70 |  | OMM | --- | Communications | Close Out Submittal | Operation & Maintenance Manual for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
71 |  | OMM | --- | Communications | Close Out Submittal | Operation & Maintenance Manual for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
72 |  | OMM | --- | Communications | Close Out Submittal | Operation & Maintenance Manual for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | CMMON USE SYSTEM |  | --- |  |  |  |  | --- | --- | ---
73 |  | OTM | --- | Communications | Close Out Submittal | Operation Training Manual for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
74 |  | OTM | --- | Communications | Close Out Submittal | Operation Training Manual for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
75 |  | OTM | --- | Communications | Close Out Submittal | Operation Training Manual for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
76 |  | Warranty | --- | Communications | Close Out Submittal | Warranty for Public Address and Voice Alarm System | SONIC ELECTRONICS | PAS |  | --- |  |  |  |  | --- | --- | ---
77 |  | Warranty | --- | Communications | Close Out Submittal | Warranty for Border Control System | SITA | BCE |  | --- |  |  |  |  | --- | --- | ---
78 |  | Warranty | --- | Communications | Close Out Submittal | Warranty for Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
79 |  | ITP | --- | Communications | Project Submittal | ITP for the installation of Common Use Systems (CUTE, CUSS, CUPPS, Boarding Pass Validation) | HP | COMMON USE SYSTEMS |  | --- |  |  |  |  | --- | --- | ---
80 |  | PQ | --- | General | Project Submittal | Prequalification of Subcontractor for LEVION | ANIXTER | SPECIAL AIRPORT SYSTEM |  | ATLS-004-PQM-ICT-00008-R01 | 1 | 2025-05-23 | ATV-1300000403-PAS-ICT-00010 | 2025-05-15 | AR (ATJV) | 17 | 17 | ATLS-004-PQM-ICT-00008-R00 | 2025-05-01 | ATV-1300000403-PQM-ICT-00010-R00 | 2025-05-01 | ATV-1300000403-PAS-ICT-00010 | 2025-05-15 | Code 3 |  | ATLS-004-PQM-ICT-00008-R01 | 2025-05-23 |  |  |  |  | AR (ATJV)
81 |  | MST | --- | Communications | Project Submittal | Method Statement for Installation of Cable Tray, Trunk and Basket Tray for Telecommunication System | SAFELINE | CRFE | Ibrar | ATLS-004-MST-ICT-00003-R00 | 0 | 2025-05-22 | ATV-1300000403-MST-ICT-00001-R00 | 2025-06-02 | Code 2 | 11 | 11 | ATLS-004-MST-ICT-00003-R00 | 2025-05-22 | ATV-1300000403-MST-ICT-00001-R00 | 2025-05-26 | ATV-1300000403-MST-ICT-00001-R00 | 2025-06-02 | Code 2
82 |  | MST | --- | Communications | Project Submittal | Method Statement for Installation of Raceways, Boxes and Accessories for Telecommunication System | SAFELINE | CRFE | Ibrar | ATLS-004-MST-ICT-00001-R00 | 0 | 2025-05-26 |  |  | AR (ATJV) | 14 | 14 | ATLS-004-MST-ICT-00001-R00 | 2025-05-26 |  |  |  |  | AR (ATJV)
83 |  | MST | --- |  | Project Submittal | Method Statement for Installation of Rack Cbinets & PDU (AR) | LEGRAND | CRFE |  | ATLS-004-MST-ICT-00012-R00 | 0 | 2025-05-26 |  |  | AR (ATJV) | 14 | 14 | ATLS-004-MST-ICT-00012-R00 | 2025-05-26 |  |  |  |  | AR (ATJV)
84 |  | MST | --- | Communications | Project Submittal | Method Statement for Installation of Floor Trunking and Junction Box For Telecommunication System | SAFELINE | CRFE | Ibrar | ATLS-004-MST-ICT-00002-R00 | 0 | 2025-05-26 |  |  | AR (ATJV) | 14 | 14 | ATLS-004-MST-ICT-00002-R00 | 2025-05-26 |  |  |  |  | AR (ATJV)
85 |  | MTS | --- | Communications | Project Submittal | Material Submittal for Racks & PDU (AR) | LEGRAND | CRFE |  | ATLS-004-MTS-ICT-00008-R00 | 0 | 2025-06-04 |  |  | AR (ATJV) | 5 | 5 | ATLS-004-MTS-ICT-00008-R00 | 2025-06-04 |  |  |  |  | AR (ATJV)
86 |  | MTS | --- | Communications | Project Submittal | Material Submittal for UPS | ANIXTER | CRFE |  | ATLS-004-MTS-ICT-00024-R00 | 0 | 2025-05-30 | ATV-1300000403-MTS-ICT-00024-R00 | 2025-06-02 | Code 2 | 3 | 3 | ATLS-004-MTS-ICT-00024-R00 | 2025-05-30 | ATV-1300000403-MTS-ICT-00024-R00 | 2025-05-31 | ATV-1300000403-MTS-ICT-00024-R00 | 2025-06-02 | Code 2
87 |  | PQ | --- | General | Project Submittal | Prequalification of Subcontractor for LEGRAND | ANIXTER | LEGRAND |  | ATLS-004-PQM-ICT-00009-R00 | 0 | 2025-05-16 | ATV-1300000403-PQM-ICT-00011 | 2025-05-26 | Code 2 | 10 | 10 | ATLS-004-PQM-ICT-00009-R00 | 2025-05-16 | ATV-1300000403-PQM-ICT-00011-R00 | 2025-05-18 | ATV-1300000403-PQM-ICT-00011 | 2025-05-26 | Code 2
88 |  | ITP | --- | Communications | Project Submittal | ITP for Installation of Cable Tray, Trunk and Basket Tray for Telecommunication System | SAFELINE | CRFE |  | ATLS-004-ITP-ICT-00001-R00 | 0 | 2025-05-20 |  |  | UR (DAR) | 20 | 20 | ATLS-004-ITP-ICT-00001-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00003-R00 | 2025-05-29 |  |  | UR (DAR)
89 |  | ITP | --- | Communications | Project Submittal | ITP for Installation of Raceways, Boxes and Accessories for Telecommunication System | SAFELINE | CRFE |  | ATLS-004-ITP-ICT-00003-R00 | 0 | 2025-05-20 |  |  | UR (DAR) | 20 | 20 | ATLS-004-ITP-ICT-00003-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00012-R00 | 2025-05-31 |  |  | UR (DAR)
90 |  | ITP | --- | Communications | Project Submittal | ITP for Installation of Racks & PDU (AR) | LEGRAND | CRFE |  | ATLS-004-ITP-ICT-00010-R00 | 0 | 2025-05-23 |  |  | UR (DAR) | 17 | 17 | ATLS-004-ITP-ICT-00010-R00 | 2025-05-23 | ATV-1300000403-ITP-ICT-00004-R00 | 2025-05-29 |  |  | UR (DAR)
91 |  | ITP | --- | Communications | Project Submittal | ITP for Installation of Floor Trunking and Junction Box For Telecommunication System | SAFELINE | CRFE |  | ATLS-004-ITP-ICT-00004-R00 | 0 | 2025-05-20 |  |  | UR (DAR) | 20 | 20 | ATLS-004-ITP-ICT-00004-R00 | 2025-05-20 | ATV-1300000403-ITP-ICT-00009-R00 | 2025-05-31 |  |  | UR (DAR)
92 |  | PQ | --- | General | Project Submittal | Prequalification of Manufacturer For Closed Circuit Television Storage (CCTV Storage) - HUAWEI KSA | HUAWEI | SPECIAL AIRPORT SYSTEM |  | ATLS-004-PQM-ICT-00006-R01 | 1 | 2025-05-01 | ATV-1300000403-PQM-ICT-00009-R00 | 2025-04-28 | AR (ATJV) | 39 | 39 | ATLS-004-PQM-ICT-00006-R00 | 2025-04-24 | ATV-1300000403-PQM-ICT-00009-R00 | 2025-04-26 | ATV-1300000403-PQM-ICT-00009-R00 | 2025-04-28 | Code 3 |  | ATLS-004-PQM-ICT-00006-R01 | 2025-05-01 |  |  |  |  | AR (ATJV)
93 |  | PQ | --- | General | Project Submittal | Prequalifiction of Manufacturer for NAFCO | NAFFCO | Fire Alarm System, Public Address System, |  | ATLS-004-PQM-ICT-00010-R00 | 0 | 2025-05-28 | ATV-1300000403-PQM-ICT-00012-R00 | 2025-06-01 | Code 3 | 4 | 4 | ATLS-004-PQM-ICT-00010-R00 | 2025-05-28 | ATV-1300000403-PQM-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-PQM-ICT-00012-R00 | 2025-06-01 | Code 3
94 |  | MTS | --- | General | Project Submittal | Material Submittal for Connectivity Hub for with Mic for recording | ANIXTER | FAS |  | ATLS-004-MTS-ICT-00025-R00 | 0 | 2025-06-02 |  |  | UR (DAR) | 7 | 7 | ATLS-004-MTS-ICT-00025-R00 | 2025-06-02 | ATV-1300000403-MTS-ICT-00026-R00 | 2025-06-04 |  |  | UR (DAR)
95 |  | PQ | --- | General | Project Submittal | Prequalifiction of Manufacturer for Safeline | Safeline | CRFE |  | ATLS-004-PQM-ICT-00011-R00 | 0 | 2025-06-04 |  |  | AR (ATJV) | 5 | 5 | ATLS-004-PQM-ICT-00011-R00 | 2025-06-04 |  |  |  |  | AR (ATJV)

## T_SDLog
SN | Sys | Sub Sys | PN | Sub Con | BN | FL | DZ | Dec | Sub-Dec | DS | DN | Column1 | Title | 21 | REV_TIME | REV_OD | 25 | S_DATE | 27 | 28 | C_DATE | 292 | C_STATUS | BY2 | AREF_0 | ASUB_0 | ASUB_02 | ASUB_03 | JVREF_0 | JVC_0 | JVCD_0 | CMAC_0 | AREF_1 | ASUB_1 | JVREF_1 | JVC_1 | JVCD_1 | CMAC_1 | AREF_2 | ASUB_2 | JVREF_2 | JVC_2 | JVCD_2 | CMAC_2 | AREF_3 | ASUB_3 | JVREF_3 | JVC_3 | JVCD_3 | CMAC_3 | AREF_4 | ASUB_4 | JVREF_4 | JVC_4 | JVCD_4 | CMAC_4 | AREF_5 | ASUB_5 | JVREF_5 | JVC_5 | JVCD_5 | CMAC_5 | AREF_6 | ASUB_6 | JVREF_6 | JVC_6 | JVCD_6 | CMAC_6 | AREF_7 | ASUB_7 | JVREF_7 | JVC_7 | JVCD_7 | CMAC_7
1 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B02-GF-00-ICT-CNT-SD-00 | Ground Floor Contaiment Overall Plan | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00009-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00009-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
2 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B02-GF-01-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part 01 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00009-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00009-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
3 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B02-GF-02-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part 02 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00009-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00009-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
4 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B02-GF-03-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part 03 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00009-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00009-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
5 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-01-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-01 | 2025-05-16 | 6 | --- | 0 | 45797 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 2025-05-26 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
6 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-02-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-02 | 2025-05-16 | 6 | --- | 0 | 45797 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 2025-05-26 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
7 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-03-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-03 | 2025-05-16 | 6 | --- | 0 | 45797 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 2025-05-26 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
8 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-04-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-04 | 2025-05-16 | 6 | --- | 0 | 45797 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 2025-05-26 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
9 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-08-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-08 | 2025-05-16 | 6 | --- | 0 | 45797 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 2025-05-26 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
10 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-12-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-12 | 2025-05-16 | 6 | --- | 0 | 45797 | ATLS-004-SD-ICT-00005-R00 | Code 2 | 26 may 25 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 |  | ATLS-004-SD-ICT-00005-R00 | 2025-05-20 | ATV-1300000403-SDS-ICT-00008-R00 | 2025-05-24 | ATV-1300000403-SDS-ICT-00008-R00 | Code 2 | 2025-05-26 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
11 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B07 | 00 | 0 | ICT | ENL | SD | 0 | 1300403-ATS-B07-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-06-11 | --- | --- |  | --- |  | Code 2 | --- |  | Code 2 | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
12 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B07 | GF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B07-GF-00-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
13 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B07 | GF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B07-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
14 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B07 | GF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B07-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
15 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B07 | GF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B07-GF-00-ICT-SEC-SD-00 | Ground Floor Ip Cctv Systems Plan | 2025-05-30 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00016-R00 | Code 2 | 01 Jun 25 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 |  | ATLS-004-SD-ICT-00016-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00011-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
16 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B07 | GF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B07-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
17 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B07 | GF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B07-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
18 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B07 | 00 | 0 | ICT | SLD | SD | 0 | 1300403-ATS-B07-00-00-ICT-SLD-SD-00 | Low Current Systems Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
19 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B07 | 00 | 0 | ICT | SLD | SD | 1 | 1300403-ATS-B07-00-00-ICT-SLD-SD-01 | Ip Cctv & Access Control Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
20 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B06 | 00 | 0 | ICT | ENL | SD | 0 | 1300403-ATS-B06-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
21 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B06 | GF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B06-GF-00-ICT-FAS-SD-00 | Ground And Roof Top Floor Fire Alarm System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
22 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B06 | GF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B06-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
23 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B06 | GF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B06-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
24 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B06 | GF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B06-GF-00-ICT-SEC-SD-00 | Ground Floor Ip Cctv System Plan | 2025-05-30 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00016-R00 | Code 2 | 01 Jun 25 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 |  | ATLS-004-SD-ICT-00016-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00011-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00011-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
25 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B06 | GF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B06-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
26 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B06 | GF | 0 | ICT | MCK | SD | 0 | 1300403-ATS-B06-GF-00-ICT-MCK-SD-00 | Ground Floor Ip Master Clock System Plan | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00030-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00030-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00024-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
27 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B06 | GF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B06-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
28 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B06 | 00 | 0 | ICT | SLD | SD | 0 | 1300403-ATS-B06-00-00-ICT-SLD-SD-00 | Low Current Systems Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
29 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B06 | 00 | 0 | ICT | SLD | SD | 1 | 1300403-ATS-B06-00-00-ICT-SLD-SD-01 | Ip Cctv , Access Control & Ip Master Clock Single-Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
30 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B05 | 00 | 0 | ICT | ENL | SD | 0 | 1300403-ATS-B05-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
31 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B05-LF-00-ICT-FAS-SD-00 | Lower Floor Fire Overall Plan At Level -1.5 And Level -5.0M Fire Alarm System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
32 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B05-LF-01-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
33 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B05-LF-02-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
34 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B05-LF-03-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
35 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B05 | LF | 4 | ICT | FAS | SD | 0 | 1300403-ATS-B05-LF-04-ICT-FAS-SD-00 | Lower Floor Fire At Level -1.5 And Level -5.0M Fire Alarm System Plan Part-04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
36 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B05-LF-00-ICT-ACS-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Access Control System Plan |  | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00014-R01 | AR (ATJV) | 02 Jun 2025 | ATV-1300000403-SDS-ICT-00016-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
37 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B05-LF-01-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-01 |  | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00014-R01 | AR (ATJV) | 02 Jun 2025 | ATV-1300000403-SDS-ICT-00016-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
38 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B05-LF-02-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-02 |  | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00014-R01 | AR (ATJV) | 02 Jun 2025 | ATV-1300000403-SDS-ICT-00016-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
39 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B05-LF-03-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-03 |  | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00014-R01 | AR (ATJV) | 02 Jun 2025 | ATV-1300000403-SDS-ICT-00016-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
40 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B05 | LF | 4 | ICT | ACS | SD | 0 | 1300403-ATS-B05-LF-04-ICT-ACS-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Access Control System Plan Part-04 |  | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00014-R01 | AR (ATJV) | 02 Jun 2025 | ATV-1300000403-SDS-ICT-00016-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00014-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00016-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00016-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00014-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
41 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B05-LF-00-ICT-COM-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Communication Equipment System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
42 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B05-LF-01-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-01 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
43 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B05-LF-02-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
44 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B05-LF-03-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-03 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
45 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B05 | LF | 4 | ICT | COM | SD | 0 | 1300403-ATS-B05-LF-04-ICT-COM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Communication Equipment System Plan Part-04 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
46 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B05-LF-00-ICT-CNT-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Overall Contaiment Plan | 2025-05-25 |  |  | 0 | 45806 | ATLS-004-SD-ICT-00023-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00023-R00 | 2025-05-29 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
47 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B05-LF-01-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-01 | 2025-05-25 |  |  | 0 | 45806 | ATLS-004-SD-ICT-00023-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00023-R00 | 2025-05-29 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
48 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B05-LF-02-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-02 | 2025-05-25 |  |  | 0 | 45806 | ATLS-004-SD-ICT-00023-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00023-R00 | 2025-05-29 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
49 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B05-LF-03-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-03 | 2025-05-25 |  |  | 0 | 45806 | ATLS-004-SD-ICT-00023-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00023-R00 | 2025-05-29 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
50 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B05 | LF | 4 | ICT | CNT | SD | 0 | 1300403-ATS-B05-LF-04-ICT-CNT-SD-00 | Lower Floor Plan At Level -1.5 And Level -5.0M Contaiment Plan Part-04 | 2025-05-25 |  |  | 0 | 45806 | ATLS-004-SD-ICT-00023-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00023-R00 | 2025-05-29 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
51 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B05-LF-00-ICT-DAT-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Data Network System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
52 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B05-LF-01-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 01 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
53 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B05-LF-02-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 02 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
54 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B05-LF-03-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 03 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
55 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B05 | LF | 4 | ICT | DAT | SD | 0 | 1300403-ATS-B05-LF-04-ICT-DAT-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Data Network System Plan Part 04 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
56 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B05-LF-00-ICT-SEC-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan | 2025-05-30 |  |  | 0 | 45807 | ATLS-004-SD-ICT-00025-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00025-R00 | 2025-05-30 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
57 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B05-LF-01-ICT-SEC-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 01 | 2025-05-30 |  |  | 0 | 45807 | ATLS-004-SD-ICT-00025-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00025-R00 | 2025-05-30 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
58 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B05-LF-02-ICT-SEC-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 02 | 2025-05-30 |  |  | 0 | 45807 | ATLS-004-SD-ICT-00025-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00025-R00 | 2025-05-30 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
59 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B05-LF-03-ICT-SEC-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 03 | 2025-05-30 |  |  | 0 | 45807 | ATLS-004-SD-ICT-00025-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00025-R00 | 2025-05-30 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
60 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B05 | LF | 4 | ICT | SEC | SD | 0 | 1300403-ATS-B05-LF-04-ICT-SEC-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Ip Video Surveillance System Plan Part 04 | 2025-05-30 |  |  | 0 | 45807 | ATLS-004-SD-ICT-00025-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00025-R00 | 2025-05-30 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
61 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B05 | LF | 0 | ICT | CPM | SD | 0 | 1300403-ATS-B05-LF-00-ICT-CPM-SD-00 | Lower Floor Overall Plan At Level -1.5 And Level -5.0M Car Parking Management System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
62 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B05 | LF | 1 | ICT | CPM | SD | 0 | 1300403-ATS-B05-LF-01-ICT-CPM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Car Parking Management System Plan Part 01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
63 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B05 | LF | 2 | ICT | CPM | SD | 0 | 1300403-ATS-B05-LF-02-ICT-CPM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Car Parking Management System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
64 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B05 | LF | 3 | ICT | CPM | SD | 0 | 1300403-ATS-B05-LF-03-ICT-CPM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Car Parking Management System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
65 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B05 | LF | 4 | ICT | CPM | SD | 0 | 1300403-ATS-B05-LF-04-ICT-CPM-SD-00 | Lower Floor At Level -1.5 And Level -5.0M Car Parking Management System Plan Part 04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
66 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 0 | ICT | SLD | SD | 0 | 1300403-ATS-B05-00-00-ICT-SLD-SD-00 | Fire Alarm System Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
67 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 0 | ICT | SLD | SD | 1 | 1300403-ATS-B05-00-00-ICT-SLD-SD-01 | Ict Data Network & Bms Single Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
68 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 0 | ICT | SLD | SD | 2 | 1300403-ATS-B05-00-00-ICT-SLD-SD-02 | Ict Rooms Detailed Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
69 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 0 | ICT | SLD | SD | 3 | 1300403-ATS-B05-00-00-ICT-SLD-SD-03 | Access Control & Ip Cctv System Single-Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
70 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 0 | ICT | SLD | SD | 4 | 1300403-ATS-B05-00-00-ICT-SLD-SD-04 | Ict Backbone Network Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
71 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B05 | 00 | 0 | ICT | SLD | SD | 5 | 1300403-ATS-B05-00-00-ICT-SLD-SD-05 | Car Parking Management System (Cpms) Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
72 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B04 | 00 | 0 | ICT | ENL | SD | 0 | 1300403-ATS-B04-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
73 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B04-LF-00-ICT-FAS-SD-00 | Lower Floor Overall Level Fire Alarm System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
74 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B04-LF-01-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
75 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B04-LF-02-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
76 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B04-LF-03-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
77 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | LF | 4 | ICT | FAS | SD | 0 | 1300403-ATS-B04-LF-04-ICT-FAS-SD-00 | Lower Floor Fire Alarm System Plan Part 04 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
78 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B04-UF-00-ICT-FAS-SD-00 | Upper Floor Overall Level Fire Alarm System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
79 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B04-UF-01-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
80 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B04-UF-02-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
81 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B04-UF-03-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
82 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B04 | UF | 4 | ICT | FAS | SD | 0 | 1300403-ATS-B04-UF-04-ICT-FAS-SD-00 | Upper Floor Fire Alarm System Plan Part 04 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
83 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B04-LF-00-ICT-COM-SD-00 | Lower Level Floor Overall Communication Equipment Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
84 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B04-LF-01-ICT-COM-SD-00 | Lower Level Floor Communication Equipment Plan Part 01 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
85 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B04-LF-02-ICT-COM-SD-00 | Lower Level Floor Communication Equipment Plan Part 02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
86 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | LF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B04-LF-03-ICT-COM-SD-00 | Lower Level Floor Communication Equipment Plan Part 03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
87 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B04-UF-00-ICT-COM-SD-00 | Upper Level Floor Overall Communication Equipment Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
88 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B04-UF-01-ICT-COM-SD-00 | Upper Level Floor Communication Equipment Plan Part 01 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
89 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B04-UF-02-ICT-COM-SD-00 | Upper Level Floor Communication Equipment Plan Part 02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
90 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B04 | UF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B04-UF-03-ICT-COM-SD-00 | Upper Level Floor Communication Equipment Plan Part 03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
91 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B04-LF-00-ICT-CNT-SD-00 | Lower Floor Overall Level Contaiment Plan | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
92 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B04-LF-01-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 01 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
93 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B04-LF-02-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 02 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
94 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B04-LF-03-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 03 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
95 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | LF | 4 | ICT | CNT | SD | 0 | 1300403-ATS-B04-LF-04-ICT-CNT-SD-00 | Lower Floor Contaiment Plan Part 04 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
96 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B04-UF-00-ICT-CNT-SD-00 | Upper Floor Overall Level Contaiment Plan | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
97 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B04-UF-01-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 01 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
98 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B04-UF-02-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 02 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
99 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B04-UF-03-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 03 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
100 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B04 | UF | 4 | ICT | CNT | SD | 0 | 1300403-ATS-B04-UF-04-ICT-CNT-SD-00 | Upper Floor Contaiment Plan Part 04 | 2025-05-25 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00019-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00019-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
101 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B04-LF-00-ICT-DAT-SD-00 | Lower Floor Overall Level Data Network System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
102 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B04-LF-01-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 01 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
103 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B04-LF-02-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 02 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
104 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B04-LF-03-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 03 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
105 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | LF | 4 | ICT | DAT | SD | 0 | 1300403-ATS-B04-LF-04-ICT-DAT-SD-00 | Lower Floor Data Network System Plan Part 04 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
106 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B04-UF-00-ICT-DAT-SD-00 | Upper Floor Overall Level Data Network System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
107 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B04-UF-01-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 01 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
108 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B04-UF-02-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 02 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
109 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B04-UF-03-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 03 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
110 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B04 | UF | 4 | ICT | DAT | SD | 0 | 1300403-ATS-B04-UF-04-ICT-DAT-SD-00 | Upper Floor Data Network System Plan Part 04 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
111 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B04-LF-00-ICT-SEC-SD-00 | Lower Floor Overall Level Ip Cctv System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
112 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B04-LF-01-ICT-SEC-SD-00 | Lower Floor Ip Cctv System Plan Part 01 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
113 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B04-LF-02-ICT-SEC-SD-00 | Lower Floor Ip Cctv System Plan Part 02 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
114 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B04-LF-03-ICT-SEC-SD-00 | Lower Floor Ip Cctv System Plan Part 03 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
115 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | LF | 4 | ICT | SEC | SD | 0 | 1300403-ATS-B04-LF-04-ICT-SEC-SD-00 | Lower Floor Ip Cctv System Plan Part 04 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
116 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B04-UF-00-ICT-SEC-SD-00 | Upper Floor Overall Level Ip Cctv System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
117 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B04-UF-01-ICT-SEC-SD-00 | Upper Floor Ip Cctv System Plan Part 01 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
118 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B04-UF-02-ICT-SEC-SD-00 | Upper Floor Ip Cctv System Plan Part 02 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
119 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B04-UF-03-ICT-SEC-SD-00 | Upper Floor Ip Cctv System Plan Part 03 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
120 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B04 | UF | 4 | ICT | SEC | SD | 0 | 1300403-ATS-B04-UF-04-ICT-SEC-SD-00 | Upper Floor Ip Cctv System Plan Part 04 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
121 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | LF | 0 | ICT | CPM | SD | 0 | 1300403-ATS-B04-LF-00-ICT-CPM-SD-00 | Lower Floor Overall Level Car Parking Mangement System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
122 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | LF | 1 | ICT | CPM | SD | 0 | 1300403-ATS-B04-LF-01-ICT-CPM-SD-00 | Lower Floor Car Parking Mangement System Plan Part 01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
123 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | LF | 2 | ICT | CPM | SD | 0 | 1300403-ATS-B04-LF-02-ICT-CPM-SD-00 | Lower Floor Car Parking Mangement System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
124 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | LF | 3 | ICT | CPM | SD | 0 | 1300403-ATS-B04-LF-03-ICT-CPM-SD-00 | Lower Floor Car Parking Mangement System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
125 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | LF | 4 | ICT | CPM | SD | 0 | 1300403-ATS-B04-LF-04-ICT-CPM-SD-00 | Lower Floor Car Parking Mangement System Plan Part 04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
126 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | UF | 0 | ICT | CPM | SD | 0 | 1300403-ATS-B04-UF-00-ICT-CPM-SD-00 | Upper Floor Overall Level Car Parking Mangement System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
127 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | UF | 1 | ICT | CPM | SD | 0 | 1300403-ATS-B04-UF-01-ICT-CPM-SD-00 | Upper Floor Car Parking Mangement System Plan Part 01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
128 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | UF | 2 | ICT | CPM | SD | 0 | 1300403-ATS-B04-UF-02-ICT-CPM-SD-00 | Upper Floor Car Parking Mangement System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
129 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | UF | 3 | ICT | CPM | SD | 0 | 1300403-ATS-B04-UF-03-ICT-CPM-SD-00 | Upper Floor Car Parking Mangement System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
130 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | UF | 4 | ICT | CPM | SD | 0 | 1300403-ATS-B04-UF-04-ICT-CPM-SD-00 | Upper Floor Car Parking Mangement System Plan Part 04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
131 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | RF | 0 | ICT | CPM | SD | 0 | 1300403-ATS-B04-RF-00-ICT-CPM-SD-00 | Roof Floor Overall Level Car Parking Mangement System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
132 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | RF | 2 | ICT | CPM | SD | 0 | 1300403-ATS-B04-RF-02-ICT-CPM-SD-00 | Roof Floor Car Parking Mangement System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
133 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | RF | 3 | ICT | CPM | SD | 0 | 1300403-ATS-B04-RF-03-ICT-CPM-SD-00 | Roof Floor Car Parking Mangement System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
134 | ICT | CAR PARKING MANAGEMENT SYSTEM | 1300403 | ATS | B04 | RF | 4 | ICT | CPM | SD | 0 | 1300403-ATS-B04-RF-04-ICT-CPM-SD-00 | Roof Floor Car Parking Mangement System Plan Part 04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
135 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 0 | ICT | SLD | SD | 0 | 1300403-ATS-B04-00-00-ICT-SLD-SD-00 | Fire Alarm System Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
136 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 0 | ICT | SLD | SD | 1 | 1300403-ATS-B04-00-00-ICT-SLD-SD-01 | Ict Backbone Network Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
137 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 0 | ICT | SLD | SD | 2 | 1300403-ATS-B04-00-00-ICT-SLD-SD-02 | Ict Rooms Detailed Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
138 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 0 | ICT | SLD | SD | 3 | 1300403-ATS-B04-00-00-ICT-SLD-SD-03 | Access Control & Ip Cctv System Single-Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
139 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 0 | ICT | SLD | SD | 4 | 1300403-ATS-B04-00-00-ICT-SLD-SD-04 | Ict Data Network Single Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
140 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B04 | 00 | 0 | ICT | SLD | SD | 5 | 1300403-ATS-B04-00-00-ICT-SLD-SD-05 | Car Parking Management System (Cpms ) Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
141 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B04-LF-00-ICT-ACS-SD-00 | Lower Floor Overall Level Access Control System Plan | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
142 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B04-LF-01-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 01 | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
143 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B04-LF-02-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 02 | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
144 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B04-LF-03-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 03 | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
145 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | LF | 4 | ICT | ACS | SD | 0 | 1300403-ATS-B04-LF-04-ICT-ACS-SD-00 | Lower Floor Access Control System Plan Part 04 | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
146 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B04-UF-00-ICT-ACS-SD-00 | Upper Floor Overall Level Access Control System Plan | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
147 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B04-UF-01-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 01 |  | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
148 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B04-UF-02-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 02 | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
149 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B04-UF-03-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 03 | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
150 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B04 | UF | 4 | ICT | ACS | SD | 0 | 1300403-ATS-B04-UF-04-ICT-ACS-SD-00 | Upper Floor Access Control System Plan Part 04 | 2025-05-26 | -1 | --- | 1 | 45811 | ATLS-004-SD-ICT-00028-R01 | AR (ATJV) | 02 Jun 25 | ATV-1300000403-SDS-ICT-00017-R00 | AR (ATJV) |  | ATLS-004-SD-ICT-00028-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00017-R00 | Code 3 | 2025-06-02 | Code 3 | ATLS-004-SD-ICT-00028-R01 | 2025-06-03 |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
151 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B03 | 00 | 0 | ICT | ENL | SD | 0 | 1300403-ATS-B03-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plan | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
152 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B03 | BF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B03-BF-00-ICT-FAS-SD-00 | Basement Fire Alarm System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
153 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B03 | GF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B03-GF-00-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
154 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B03 | FF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B03-FF-00-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
155 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B03 | BF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B03-BF-00-ICT-PAS-SD-00 | Basement Sound Managment System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
156 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B03 | GF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B03-GF-00-ICT-PAS-SD-00 | Ground Floor Sound Management System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
157 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B03 | FF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B03-FF-00-ICT-PAS-SD-00 | First Floor Sound Management System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
158 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B03 | BF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B03-BF-00-ICT-DAT-SD-00 | Basement Data Network Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
159 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B03 | GF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B03-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
160 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B03 | FF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B03-FF-00-ICT-DAT-SD-00 | First Floor Data Network Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
161 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B03 | BF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B03-BF-00-ICT-SEC-SD-00 | Basement Ip Cctv System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
162 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B03 | GF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B03-GF-00-ICT-SEC-SD-00 | Ground Floor Ip Cctv System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
163 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B03 | FF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B03-FF-00-ICT-SEC-SD-00 | First Floor Ip Cctv System Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
164 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 0 | ICT | SLD | SD | 0 | 1300403-ATS-B03-00-00-ICT-SLD-SD-00 | Fire Alarm System Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
165 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 0 | ICT | SLD | SD | 1 | 1300403-ATS-B03-00-00-ICT-SLD-SD-01 | Sound Management System Single-Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
166 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 0 | ICT | SLD | SD | 2 | 1300403-ATS-B03-00-00-ICT-SLD-SD-02 | Ict Network & Bms Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
167 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 0 | ICT | SLD | SD | 3 | 1300403-ATS-B03-00-00-ICT-SLD-SD-03 | Access Control System Single-Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
168 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 0 | ICT | SLD | SD | 4 | 1300403-ATS-B03-00-00-ICT-SLD-SD-04 | Ict Rooms Detailed Layouts | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
169 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 0 | ICT | SLD | SD | 5 | 1300403-ATS-B03-00-00-ICT-SLD-SD-05 | Disabled Alarm Toilet Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
170 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B03 | 00 | 0 | ICT | SLD | SD | 6 | 1300403-ATS-B03-00-00-ICT-SLD-SD-06 | Ip Cctv Single Line Diagram | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
171 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B03 | BF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B03-BF-00-ICT-ACS-SD-00 | Basement Access Control System Plan | 2025-05-26 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00029-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00029-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
172 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B03 | GF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B03-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Plan | 2025-05-26 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00029-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00029-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
173 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B03 | BF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B03-BF-00-ICT-TEL-SD-00 | Basement Floor Ip Telephone System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
174 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B03 | GF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B03-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
175 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B03 | BF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B03-BF-00-ICT-COM-SD-00 | Basement Floor Communication Equipment Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
176 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B03 | GF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B03-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
177 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B02 | 00 | 0 | ICT | ENL | SD | 0 | 1300403-ATS-B02-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans (1 Of 2) | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
178 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B02 | 00 | 0 | ICT | ENL | SD | 1 | 1300403-ATS-B02-00-00-ICT-ENL-SD-01 | Ict Technical Rooms Enlarged Plans (2 Of 2) | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
179 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B02-GF-00-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Overall Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
180 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B02-GF-01-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan Part 01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
181 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B02-GF-02-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan Part 02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
182 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B02-GF-03-ICT-FAS-SD-00 | Ground Floor Fire Alarm System Plan Part 03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
183 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B02-FF-00-ICT-FAS-SD-00 | First Floor Fire Alarm System Overall Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
184 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B02-FF-01-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part 01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
185 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B02-FF-02-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part 02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
186 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B02-FF-03-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part 03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
187 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | RF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B02-RF-00-ICT-FAS-SD-00 | Roof Fire Alarm System Overall Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
188 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | RF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B02-RF-01-ICT-FAS-SD-00 | Roof Fire Alarm System Plan Part 01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
189 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B02 | RF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B02-RF-02-ICT-FAS-SD-00 | Roof Fire Alarm System Plan Part 02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
190 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B02-GF-00-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Overall Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
191 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | PAS | SD | 0 | 1300403-ATS-B02-GF-01-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Plan Part 01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
192 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | PAS | SD | 0 | 1300403-ATS-B02-GF-02-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Plan Part 02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
193 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | PAS | SD | 0 | 1300403-ATS-B02-GF-03-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification System Plan Part 03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
194 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B02-FF-00-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Overall Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
195 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | PAS | SD | 0 | 1300403-ATS-B02-FF-01-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part 01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
196 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | PAS | SD | 0 | 1300403-ATS-B02-FF-02-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part 02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
197 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | PAS | SD | 0 | 1300403-ATS-B02-FF-03-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part 03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
198 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B02-GF-00-ICT-COM-SD-00 | Ground Floor Communication Equipment Overall Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
199 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B02-GF-01-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan Part 01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
200 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B02-GF-02-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan Part 02 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
201 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B02-GF-03-ICT-COM-SD-00 | Ground Floor Communication Equipment Plan Part 03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
202 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B02-FF-00-ICT-COM-SD-00 | First Floor Communication Equipment Overall Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
203 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B02-FF-01-ICT-COM-SD-00 | First Floor Communication Equipment Plan Part 01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
204 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B02-FF-02-ICT-COM-SD-00 | First Floor Communication Equipment Plan Part 02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
205 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B02-FF-03-ICT-COM-SD-00 | First Floor Communication Equipment Plan Part 03 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
206 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B02-FF-00-ICT-CNT-SD-00 | First Floor Contaiment Overall Plan | 2025-05-25 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00010-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
207 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B02-FF-01-ICT-CNT-SD-00 | First Floor Contaiment Plan Part 01 | 2025-05-25 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00010-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
208 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B02-FF-02-ICT-CNT-SD-00 | First Floor Contaiment Plan Part 02 | 2025-05-25 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00010-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
209 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B02-FF-03-ICT-CNT-SD-00 | First Floor Contaiment Plan Part 03 | 2025-05-25 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00010-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00010-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
210 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B02-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Overall Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
211 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | TEL | SD | 0 | 1300403-ATS-B02-GF-01-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan Part 01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
212 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | TEL | SD | 0 | 1300403-ATS-B02-GF-02-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan Part 02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
213 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | TEL | SD | 0 | 1300403-ATS-B02-GF-03-ICT-TEL-SD-00 | Ground Floor Ip Telephone System Plan Part 03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
214 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B02-FF-00-ICT-TEL-SD-00 | First Floor Ip Telephone System Overall Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
215 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | TEL | SD | 0 | 1300403-ATS-B02-FF-01-ICT-TEL-SD-00 | First Floor Ip Telephone System Plan Part 01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
216 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | TEL | SD | 0 | 1300403-ATS-B02-FF-02-ICT-TEL-SD-00 | First Floor Ip Telephone System Plan Part 02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
217 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 0 | 1300403-ATS-B02-00-00-ICT-SLD-SD-00 | Fire Alarm System Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
218 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 1 | 1300403-ATS-B02-00-00-ICT-SLD-SD-01 | Public Address & Voice Evacuation Systems Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
219 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 2 | 1300403-ATS-B02-00-00-ICT-SLD-SD-02 | Ict Backbone Network Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
220 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 3 | 1300403-ATS-B02-00-00-ICT-SLD-SD-03 | Ict Rooms Detailed Layouts (1 Of 2) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
221 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 4 | 1300403-ATS-B02-00-00-ICT-SLD-SD-04 | Ict Rooms Detailed Layouts (2 Of 2) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
222 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 5 | 1300403-ATS-B02-00-00-ICT-SLD-SD-05 | Ict Data Network Single Line Diagrams | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
223 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 6 | 1300403-ATS-B02-00-00-ICT-SLD-SD-06 | Ip Master Clock Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
224 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 7 | 1300403-ATS-B02-00-00-ICT-SLD-SD-07 | Disabled Toilet Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
225 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 8 | 1300403-ATS-B02-00-00-ICT-SLD-SD-08 | Ip Cctv Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
226 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 9 | 1300403-ATS-B02-00-00-ICT-SLD-SD-09 | Fids & Cids Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
227 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 10 | 1300403-ATS-B02-00-00-ICT-SLD-SD-10 | Access Control Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
228 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B02 | 00 | 0 | ICT | SLD | SD | 11 | 1300403-ATS-B02-00-00-ICT-SLD-SD-11 | Electronic Visual Information Display (Evids) And Cid Single Line Diagrams | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
229 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | MCK | SD | 0 | 1300403-ATS-B02-GF-00-ICT-MCK-SD-00 | Ground Floor Master Clock System Overall Plan | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00026-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
230 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | MCK | SD | 0 | 1300403-ATS-B02-GF-01-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part 01 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00026-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
231 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | MCK | SD | 0 | 1300403-ATS-B02-GF-02-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part 02 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00026-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
232 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | MCK | SD | 0 | 1300403-ATS-B02-GF-03-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part 03 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00026-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00026-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00022-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
233 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | MCK | SD | 0 | 1300403-ATS-B02-FF-00-ICT-MCK-SD-00 | First Floor Master Clock System Overall Plan | 2025-06-02 | 10 | --- | 0 | 45807 | ATLS-004-SD-ICT-00027-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
234 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | MCK | SD | 0 | 1300403-ATS-B02-FF-01-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part 01 | 2025-06-02 | 10 | --- | 0 | 45807 | ATLS-004-SD-ICT-00027-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
235 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | MCK | SD | 0 | 1300403-ATS-B02-FF-02-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part 02 | 2025-06-02 | 10 | --- | 0 | 45807 | ATLS-004-SD-ICT-00027-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
236 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | MCK | SD | 0 | 1300403-ATS-B02-FF-03-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part 03 | 2025-06-02 | 10 | --- | 0 | 45807 | ATLS-004-SD-ICT-00027-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00027-R00 | 2025-05-30 | ATV-1300000403-SDS-ICT-00023-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
237 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B02-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control System Overall Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
238 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B02-GF-01-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part 01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
239 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B02-GF-02-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
240 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B02-GF-03-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
241 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B02-FF-00-ICT-ACS-SD-00 | First Floor Access Control System Overall Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
242 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B02-FF-01-ICT-ACS-SD-00 | First Floor Access Control System Plan Part 01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
243 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B02-FF-02-ICT-ACS-SD-00 | First Floor Access Control System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
244 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B02-FF-03-ICT-ACS-SD-00 | First Floor Access Control System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
245 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B02-GF-00-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Overall Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
246 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B02-GF-01-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part 01 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
247 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B02-GF-02-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part 02 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
248 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B02-GF-03-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part 03 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
249 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B02-FF-00-ICT-SEC-SD-00 | First Floor Video Survelliance System Overall Plan | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
250 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B02-FF-01-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part 01 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
251 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B02-FF-02-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part 02 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
252 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B02-FF-03-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part 03 | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
253 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | WAP | SD | 0 | 1300403-ATS-B02-GF-00-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Overall Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
254 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | WAP | SD | 0 | 1300403-ATS-B02-GF-01-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part 01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
255 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | WAP | SD | 0 | 1300403-ATS-B02-GF-02-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part 02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
256 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | WAP | SD | 0 | 1300403-ATS-B02-GF-03-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part 03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
257 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | WAP | SD | 0 | 1300403-ATS-B02-FF-00-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Overall Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
258 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | WAP | SD | 0 | 1300403-ATS-B02-FF-01-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part 01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
259 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | WAP | SD | 0 | 1300403-ATS-B02-FF-02-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part 02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
260 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | WAP | SD | 0 | 1300403-ATS-B02-FF-03-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part 03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
261 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | ECS | SD | 0 | 1300403-ATS-B02-GF-00-ICT-ECS-SD-00 | Ground Floor Emergency Communication & Disabled Toilet Alarm System Overall Plan | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
262 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | ECS | SD | 0 | 1300403-ATS-B02-GF-01-ICT-ECS-SD-00 | Ground Floor Emergency Communication & Disabled Toilet Alarm System Plan Part 01 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
263 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | ECS | SD | 0 | 1300403-ATS-B02-FF-00-ICT-ECS-SD-00 | First Floor Emergency Communication & Disabled Toilet Alarm System Overall Plan | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
264 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | ECS | SD | 0 | 1300403-ATS-B02-FF-01-ICT-ECS-SD-00 | First Floor Emergency Communication & Disabled Toilet Alarm System Plan Part 01 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
265 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B02-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network System Overall Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
266 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B02-GF-01-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part 01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
267 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B02-GF-02-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
268 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B02-GF-03-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
269 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B02-FF-00-ICT-DAT-SD-00 | First Floor Data Network System Overall Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
270 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B02-FF-01-ICT-DAT-SD-00 | First Floor Data Network System Plan Part 01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
271 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B02-FF-02-ICT-DAT-SD-00 | First Floor Data Network System Plan Part 02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
272 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B02-FF-03-ICT-DAT-SD-00 | First Floor Data Network System Plan Part 03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
273 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 0 | 1300403-ATS-B01-00-00-ICT-ENL-SD-00 | Ict Technical Rooms Enlarged Plans (1 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
274 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 1 | 1300403-ATS-B01-00-00-ICT-ENL-SD-01 | Ict Technical Rooms Enlarged Plans (2 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
275 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 2 | 1300403-ATS-B01-00-00-ICT-ENL-SD-02 | Ict Technical Rooms Enlarged Plans (3 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
276 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 3 | 1300403-ATS-B01-00-00-ICT-ENL-SD-03 | Ict Technical Rooms Enlarged Plans (4 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
277 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 4 | 1300403-ATS-B01-00-00-ICT-ENL-SD-04 | Ict Technical Rooms Enlarged Plans (5 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
278 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 5 | 1300403-ATS-B01-00-00-ICT-ENL-SD-05 | Ict Technical Rooms Enlarged Plans (6 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
279 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 6 | 1300403-ATS-B01-00-00-ICT-ENL-SD-06 | Ict Technical Rooms Enlarged Plans (7 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
280 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 7 | 1300403-ATS-B01-00-00-ICT-ENL-SD-07 | Ict Technical Rooms Enlarged Plans (8 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
281 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 8 | 1300403-ATS-B01-00-00-ICT-ENL-SD-08 | Ict Technical Rooms Enlarged Plans (9 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
282 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 9 | 1300403-ATS-B01-00-00-ICT-ENL-SD-09 | Ict Technical Rooms Enlarged Plans (10 Of 10) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
283 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 10 | 1300403-ATS-B01-00-00-ICT-ENL-SD-10 | Ict Rooms Detailed Layouts (1 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
284 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 11 | 1300403-ATS-B01-00-00-ICT-ENL-SD-11 | Ict Rooms Detailed Layouts (2 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
285 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 12 | 1300403-ATS-B01-00-00-ICT-ENL-SD-12 | Ict Rooms Detailed Layouts (3 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
286 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 13 | 1300403-ATS-B01-00-00-ICT-ENL-SD-13 | Ict Rooms Detailed Layouts (4 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
287 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 14 | 1300403-ATS-B01-00-00-ICT-ENL-SD-14 | Ict Rooms Detailed Layouts (5 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
288 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 15 | 1300403-ATS-B01-00-00-ICT-ENL-SD-15 | Ict Rooms Detailed Layouts (6 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
289 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 16 | 1300403-ATS-B01-00-00-ICT-ENL-SD-16 | Ict Rooms Detailed Layouts (7 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
290 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 17 | 1300403-ATS-B01-00-00-ICT-ENL-SD-17 | Ict Rooms Detailed Layouts (8 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
291 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 18 | 1300403-ATS-B01-00-00-ICT-ENL-SD-18 | Ict Rooms Detailed Layouts (9 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
292 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 19 | 1300403-ATS-B01-00-00-ICT-ENL-SD-19 | Ict Rooms Detailed Layouts (10 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
293 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 20 | 1300403-ATS-B01-00-00-ICT-ENL-SD-20 | Ict Rooms Detailed Layouts (11 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
294 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 21 | 1300403-ATS-B01-00-00-ICT-ENL-SD-21 | Ict Rooms Detailed Layouts (12 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
295 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 22 | 1300403-ATS-B01-00-00-ICT-ENL-SD-22 | Ict Rooms Detailed Layouts (13 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
296 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 23 | 1300403-ATS-B01-00-00-ICT-ENL-SD-23 | Ict Rooms Detailed Layouts (14 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
297 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 24 | 1300403-ATS-B01-00-00-ICT-ENL-SD-24 | Ict Rooms Detailed Layouts (15 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
298 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 25 | 1300403-ATS-B01-00-00-ICT-ENL-SD-25 | Ict Rooms Detailed Layouts (16 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
299 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 26 | 1300403-ATS-B01-00-00-ICT-ENL-SD-26 | Ict Rooms Detailed Layouts (17 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
300 | ICT | ICT TECHNICAL ROOMS | 1300403 | ATS | B01 | 00 | 0 | ICT | ENL | SD | 27 | 1300403-ATS-B01-00-00-ICT-ENL-SD-27 | Ict Rooms Detailed Layouts (18 Of 18) | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
301 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-00-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm Overall System Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
302 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-01-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
303 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-02-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
304 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-03-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
305 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-04-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-04 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
306 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-05-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-05 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
307 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-06-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-06 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
308 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-07-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-07 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
309 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-08-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-08 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
310 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-09-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-09 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
311 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-10-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-10 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
312 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-11-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-11 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
313 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | FAS | SD | 0 | 1300403-ATS-B01-BF-12-ICT-FAS-SD-00 | Terminal Basement Floor Fire Alarm System Plan Part-12 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
314 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-00-ICT-FAS-SD-00 | First Floor Fire Alarm Ovrall System Plan (Departure Level) | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
315 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-01-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
316 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-02-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
317 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-03-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
318 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-04-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-04 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
319 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-05-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-05 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
320 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-06-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-06 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
321 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-07-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-07 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
322 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-08-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-08 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
323 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-09-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-09 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
324 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-10-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-10 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
325 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-11-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-11 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
326 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-12-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-12 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
327 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-13-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-13 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
328 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-14-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-14 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
329 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | FAS | SD | 0 | 1300403-ATS-B01-GF-15-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-15 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
330 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-00-ICT-FAS-SD-00 | First Floor Fire Alarm Ovrall System Plan (Departure Level) | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
331 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-01-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
332 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-02-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
333 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-03-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
334 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-04-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-04 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
335 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-05-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-05 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
336 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-06-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-06 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
337 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-07-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-07 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
338 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-08-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-08 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
339 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-09-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-09 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
340 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-10-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-10 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
341 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-11-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-11 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
342 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-12-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-12 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
343 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-13-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-13 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
344 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-14-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-14 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
345 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | FAS | SD | 0 | 1300403-ATS-B01-FF-15-ICT-FAS-SD-00 | First Floor Fire Alarm System Plan Part-15 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
346 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-FAS-SD-00 | Mezzanine Fire Alarm Overall System Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
347 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 1 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-01-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
348 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
349 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
350 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 4 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-04-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-04 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
351 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 5 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-05-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-05 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
352 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-06 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
353 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-07 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
354 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 8 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-08-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-08 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
355 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 9 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-09-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-09 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
356 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-10 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
357 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-11 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
358 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-12 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
359 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-13-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-13 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
360 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-14-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-14 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
361 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | FAS | SD | 0 | 1300403-ATS-B01-MZ-15-ICT-FAS-SD-00 | Mezzanine Fire Alarm System Plan Part-15 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
362 | ICT | FIRE ALARM SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | FAS | SD | 1 | 1300403-ATS-B01-GF-00-ICT-FAS-SD-01 | Locker Area Fire Alarm System Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
363 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-00-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification Overall System Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
364 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-01-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
365 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-02-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
366 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-03-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
367 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-04-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-04 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
368 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-05-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-05 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
369 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-06-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-06 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
370 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-07-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
371 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-08-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-08 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
372 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-09-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-09 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
373 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-10-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-10 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
374 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-11-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-11 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
375 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | PAS | SD | 0 | 1300403-ATS-B01-BF-12-ICT-PAS-SD-00 | Terminal Basement Floor Public Address And Mass Notification System Plan Part-12 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
376 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-00-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Overall System Plan (Arrival Level) | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
377 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-01-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
378 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-02-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
379 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-03-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
380 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-04-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-04 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
381 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-05-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-05 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
382 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-06-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-06 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
383 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-07-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
384 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-08-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-08 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
385 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-09-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-09 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
386 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-10-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-10 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
387 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-11-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-11 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
388 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-12-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-12 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
389 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-13-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-13 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
390 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-14-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-14 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
391 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | PAS | SD | 0 | 1300403-ATS-B01-GF-15-ICT-PAS-SD-00 | Ground Floor Public Address And Mass Notification Ystem Plan Part-15 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
392 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | 00 | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B01-00-00-ICT-PAS-SD-00 | Locker Area Public Address And Mass Notification System Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
393 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-00-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification Overall System Plan(Departure Level) | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
394 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-01-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
395 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-02-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
396 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-03-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
397 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-04-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-04 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
398 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-05-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-05 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
399 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-06-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-06 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
400 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-07-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
401 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-08-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-08 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
402 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-09-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-09 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
403 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-10-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-10 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
404 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-11-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-11 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
405 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-12-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-12 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
406 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-13-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-13 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
407 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-14-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-14 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
408 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | PAS | SD | 0 | 1300403-ATS-B01-FF-15-ICT-PAS-SD-00 | First Floor Public Address And Mass Notification System Plan Part-15 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
409 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification Overall System Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
410 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 1 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-01-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
411 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
412 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
413 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 4 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-04-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-04 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
414 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 5 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-05-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-05 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
415 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-06 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
416 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
417 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 8 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-08-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-08 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
418 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 9 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-09-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-09 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
419 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-10 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
420 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-11 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
421 | ICT | SOUND MANAGEMENT SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | PAS | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-PAS-SD-00 | Mezzanine Floor Public Address And Mass Notification System Plan Part-12 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
422 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-00-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment Overall System Plan | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
423 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-01-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-01 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
424 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-02-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-02 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
425 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-03-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-03 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
426 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-04-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-04 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
427 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-05-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-05 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
428 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-06-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-06 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
429 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-07-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-07 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
430 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-08-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-08 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
431 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-09-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-09 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
432 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-10-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-10 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
433 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-11-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-11 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
434 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | COM | SD | 0 | 1300403-ATS-B01-BF-12-ICT-COM-SD-00 | Basement Communication Eqpmnt Equipment System Plan Part-12 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00036-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00036-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
435 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-00-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment Overall System Plan(Arrival Level) | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
436 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-01-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
437 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-02-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
438 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-03-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
439 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-04-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-04 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
440 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-05-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-05 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
441 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-06-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-06 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
442 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-07-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-07 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
443 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-08-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-08 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
444 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-09-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-09 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
445 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-10-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-10 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
446 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-11-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-11 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
447 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-12-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-12 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
448 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-13-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-13 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
449 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-14-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-14 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
450 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | COM | SD | 0 | 1300403-ATS-B01-GF-15-ICT-COM-SD-00 | Ground Floor Communication Eqpmnt Equipment System Plan Part-15 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
451 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-00-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment Overall System Plan (Departure Level) | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
452 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-01-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-01 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
453 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-02-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-02 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
454 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-03-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-03 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
455 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-04-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-04 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
456 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-05-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-05 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
457 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-06-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-06 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
458 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-07-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-07 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
459 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-08-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-08 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
460 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-09-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-09 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
461 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-10-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-10 | 2025-05-18 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
462 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-11-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-11 | 2025-05-18 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
463 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-12-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-12 | 2025-06-11 |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
464 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-13-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-13 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
465 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-14-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-14 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
466 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | COM | SD | 0 | 1300403-ATS-B01-FF-15-ICT-COM-SD-00 | First Floor Communication Eqpmnt Equipment System Plan Part-15 |  |  |  | 0 | 45812 | ATLS-004-SD-ICT-00037-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00037-R00 | 2025-06-04 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
467 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Overall Equipment Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
468 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 1 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-01-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-01 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
469 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-02 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
470 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-03 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
471 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 4 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-04-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-04 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
472 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 5 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-05-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-05 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
473 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-06 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
474 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-07 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
475 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 8 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-08-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-08 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
476 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 9 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-09-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-09 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
477 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-10 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
478 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-11 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
479 | ICT | COMMUNICATION EQUIPMENT SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | COM | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-COM-SD-00 | Mezzanine Floor Communication Eqpmnt Equipment Plan Part-12 |  | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
480 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-00-ICT-CNT-SD-00 | Ground Floor Contaiment Overall Plan (Arrival Level) | 2025-05-16 |  |  | 0 | 45799 | ATLS-004-SD-ICT-00007-R00 | Code 2 | --- |  | Code 2 |  | ATLS-004-SD-ICT-00007-R00 | 2025-05-22 | ATV-1300000403-SDS-ICT-00006-R00 | 2025-05-24 |  | Code 2 |  | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
481 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-05-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-05 (AR) | 2025-05-12 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
482 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-06-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-06 (AR) | 2025-05-12 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
483 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-07-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-07 | 2025-05-16 |  |  | 0 | 45799 | ATLS-004-SD-ICT-00007-R00 | Code 2 | --- |  | Code 2 |  | ATLS-004-SD-ICT-00007-R00 | 2025-05-22 | ATV-1300000403-SDS-ICT-00006-R00 | 2025-05-24 |  | Code 2 |  | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
484 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-09-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-09 | 2025-05-12 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
485 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-10-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-10 | 2025-05-12 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00001-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 |  | ATLS-004-SD-ICT-00001-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00003-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
486 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-11-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-11 | 2025-05-16 |  |  | 0 | 45799 | ATLS-004-SD-ICT-00007-R00 | Code 2 | --- |  | Code 2 |  | ATLS-004-SD-ICT-00007-R00 | 2025-05-22 | ATV-1300000403-SDS-ICT-00006-R00 | 2025-05-24 |  | Code 2 |  | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
487 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-13-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-13 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00003-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 |  | ATLS-004-SD-ICT-00003-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
488 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-14-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-14 (AR) | 2025-05-12 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00003-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 |  | ATLS-004-SD-ICT-00003-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
489 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | CNT | SD | 0 | 1300403-ATS-B01-GF-15-ICT-CNT-SD-00 | Ground Floor Contaiment Plan Part-15 (AR) | 2025-05-12 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00003-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 |  | ATLS-004-SD-ICT-00003-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00004-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
490 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-00-ICT-CNT-SD-00 | First Floor Contaiment Overall Plan (Departure Level) | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
491 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-01-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-01 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
492 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-02-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-02 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
493 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-03-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-03 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
494 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-04-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-04 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
495 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-05-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-05 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
496 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-06-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-06 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
497 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-07-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-07 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
498 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-08-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-08 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
499 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-09-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-09 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
500 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-10-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-10 | 2025-05-12 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
501 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-11-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-11 | 2025-05-12 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
502 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-12-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-12 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
503 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-13-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-13 | 2025-05-16 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
504 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-14-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-14 | 2025-05-12 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
505 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | CNT | SD | 0 | 1300403-ATS-B01-FF-15-ICT-CNT-SD-00 | First Floor Contaiment Plan Part-15 | 2025-05-12 | 1 | --- | 0 | 45796 | ATLS-004-SD-ICT-00004-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 |  | ATLS-004-SD-ICT-00004-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | 2025-05-19 | ATV-1300000403-SDS-ICT-00005-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
506 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Overall Plan | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
507 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-01-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-01 |  | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
508 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-02 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
509 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-03 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00006-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00006-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
510 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 4 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-04-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-04 |  | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
511 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 5 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-05-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-05 |  | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
512 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-06 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
513 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-07 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00011-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00011-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
514 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 8 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-08-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-08 |  | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
515 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 9 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-09-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-09 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
516 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-10 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
517 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-11 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00012-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00012-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
518 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-12 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
519 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-13-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-13 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
520 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-14-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-14 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
521 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | CNT | SD | 0 | 1300403-ATS-B01-MZ-15-ICT-CNT-SD-00 | Mezzanine Floor Contaiment Plan Part-15 | 2025-05-22 | 2 | --- | 0 | 45804 | ATLS-004-SD-ICT-00013-R00 | Code 2 | 29 May 2025 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 |  | ATLS-004-SD-ICT-00013-R00 | 2025-05-27 | ATV-1300000403-SDS-ICT-00009-R00 | 2025-05-26 | ATV-1300000403-SDS-ICT-00009-R00 | Code 2 | 2025-05-29 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
522 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-00-ICT-TEL-SD-00 | Terminal Basement IP Telephony Overall System Plan | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
523 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-01-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
524 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-02-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-02 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
525 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-03-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-03 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
526 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-04-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-04 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
527 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-05-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-05 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
528 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-06-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-06 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
529 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-07-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-07 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
530 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-08-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-08 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
531 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-09-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-09 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
532 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-10-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-10 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
533 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-11-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-11 | 2025-06-16 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00008-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00008-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
534 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | TEL | SD | 0 | 1300403-ATS-B01-BF-12-ICT-TEL-SD-00 | Terminal Basement IP Telephony Plan Part-12 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
535 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-00-ICT-TEL-SD-00 | Ground Floor Ip Telephony Overall System Plan (Arrival Level) | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
536 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-01-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
537 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-02-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
538 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-03-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
539 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-04-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-04 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
540 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-05-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-05 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
541 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-06-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-06 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
542 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-07-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-07 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
543 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-08-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-08 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
544 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-09-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-09 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
545 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-10-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-10 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
546 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-11-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-11 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
547 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-12-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-12 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
548 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-13-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-13 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
549 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-14-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-14 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
550 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | TEL | SD | 0 | 1300403-ATS-B01-GF-15-ICT-TEL-SD-00 | Ground Floor Ip Telephony System Plan Part-15 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
551 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | 00 | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B01-00-00-ICT-TEL-SD-00 | Locker Area Ip Telephony System Plan | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
552 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-00-ICT-TEL-SD-00 | First Floor Ip Telephony Overall System Plan (Departure Level) | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
553 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-01-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-01 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
554 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-02-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-02 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
555 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-03-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-03 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
556 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-04-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-04 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
557 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-05-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-05 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
558 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-06-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-06 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
559 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-07-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-07 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
560 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-08-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-08 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
561 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-09-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-09 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
562 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-10-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-10 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
563 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-11-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-11 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
564 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-12-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-12 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
565 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-13-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-13 | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
566 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-14-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-14 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
567 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | TEL | SD | 0 | 1300403-ATS-B01-FF-15-ICT-TEL-SD-00 | First Floor Ip Telephony System Plan Part-15 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
568 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony Overall System Plan | 2025-06-16 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
569 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 1 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-01-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-01 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
570 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-02 | 2025-06-16 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
571 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-03 | 2025-06-16 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
572 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 4 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-04-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-04 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
573 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 5 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-05-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-05 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
574 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-06 | 2025-06-16 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
575 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-07 | 2025-06-16 |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
576 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 8 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-08-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-08 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
577 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 9 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-09-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-09 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
578 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-10 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
579 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-11 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
580 | ICT | IP TELEPHONE SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | TEL | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-TEL-SD-00 | Mezzanine Floor Ip Telephony System Plan Part-12 |  |  |  | 0 | 45805 | ATLS-004-SD-ICT-00018-R00 | AR (ATJV) | --- |  | AR (ATJV) |  | ATLS-004-SD-ICT-00018-R00 | 2025-05-28 |  |  |  | AR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
581 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 0 | 1300403-ATS-B01-00-00-ICT-SLD-SD-00 | Fire Alarm Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
582 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 1 | 1300403-ATS-B01-00-00-ICT-SLD-SD-01 | Public Address & Voice Evacuation System Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
583 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 2 | 1300403-ATS-B01-00-00-ICT-SLD-SD-02 | Ict Aan Telephone Network Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
584 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 3 | 1300403-ATS-B01-00-00-ICT-SLD-SD-03 | Ip Video Surveillance System Network Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
585 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 4 | 1300403-ATS-B01-00-00-ICT-SLD-SD-04 | Access Control System Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
586 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 5 | 1300403-ATS-B01-00-00-ICT-SLD-SD-05 | Master Clock System Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
587 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 6 | 1300403-ATS-B01-00-00-ICT-SLD-SD-06 | Emergency Communication System And Disabled Alarm Toilet Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
588 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 7 | 1300403-ATS-B01-00-00-ICT-SLD-SD-07 | Ict Backbone Network Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
589 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 8 | 1300403-ATS-B01-00-00-ICT-SLD-SD-08 | Ict Aan Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
590 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 9 | 1300403-ATS-B01-00-00-ICT-SLD-SD-09 | Ict Customs Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
591 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 10 | 1300403-ATS-B01-00-00-ICT-SLD-SD-10 | Ict Gdp Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
592 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 11 | 1300403-ATS-B01-00-00-ICT-SLD-SD-11 | Ict Gid Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
593 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 12 | 1300403-ATS-B01-00-00-ICT-SLD-SD-12 | Ict Intelligent Services Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
594 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 13 | 1300403-ATS-B01-00-00-ICT-SLD-SD-13 | Ict Nic_Myphone Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
595 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 14 | 1300403-ATS-B01-00-00-ICT-SLD-SD-14 | Ict Pan (Wap) Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
596 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 15 | 1300403-ATS-B01-00-00-ICT-SLD-SD-15 | Ict Rsaf Data Network Single-Line Diagram | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
597 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 16 | 1300403-ATS-B01-00-00-ICT-SLD-SD-16 | Sas Equipment Single Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
598 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 17 | 1300403-ATS-B01-00-00-ICT-SLD-SD-17 | Flight Information Dispaly System (Fids) Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
599 | ICT | SINGLE LINE DIAGRAM | 1300403 | ATS | B01 | 00 | 0 | ICT | SLD | SD | 18 | 1300403-ATS-B01-00-00-ICT-SLD-SD-18 | E-Gate Gdp Network Single-Line Diagram | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
600 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-00-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation Overall System Plan (Arrival Level) | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
601 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-01-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
602 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-02-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
603 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-05-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-05 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
604 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-06-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-06 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
605 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-09-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-09 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
606 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-10-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-10 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
607 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-13-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-13 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
608 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-14-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-14 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
609 | ICT | BAGGAGE RECONCILIATION SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | BRS | SD | 0 | 1300403-ATS-B01-GF-15-ICT-BRS-SD-00 | Ground Floor Baggage Reconciliation System Plan Part-15 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
610 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-00-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock Overall System Plan | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
611 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-01-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-01 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
612 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-02-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-02 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
613 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-03-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-03 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
614 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-04-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-04 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
615 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-05-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-05 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
616 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-06-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-06 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
617 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-07-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-07 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
618 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-08-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-08 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
619 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-09-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-09 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
620 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-10-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-10 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
621 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-11-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-11 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
622 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | MCK | SD | 0 | 1300403-ATS-B01-BF-12-ICT-MCK-SD-00 | Terminal Basement Floor Master Clock System Plan Part-12 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00015-R00 | Code 2 | 01 jun 25 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 |  | ATLS-004-SD-ICT-00015-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00010-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
623 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-00-ICT-MCK-SD-00 | Ground Floor Master Clock Overall System Plan (Arrival Level) | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
624 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-01-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-01 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
625 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-02-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-02 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
626 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-03-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-03 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
627 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-04-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-04 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
628 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-05-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-05 | 2025-05-22 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
629 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-06-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-06 | 2025-05-22 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
630 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-07-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-07 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
631 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-08-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-08 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
632 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-09-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-09 | 2025-05-22 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
633 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-10-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-10 | 2025-05-22 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
634 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-11-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-11 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
635 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-12-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-12 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
636 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-13-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-13 | 2025-06-02 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
637 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-14-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-14 | 2025-05-22 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
638 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | MCK | SD | 0 | 1300403-ATS-B01-GF-15-ICT-MCK-SD-00 | Ground Floor Master Clock System Plan Part-15 | 2025-05-22 | 4 | --- | 0 | 45805 | ATLS-004-SD-ICT-00020-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 |  | ATLS-004-SD-ICT-00020-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00013-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00013-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
639 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-00-ICT-MCK-SD-00 | First Floor Master Clock Overall System Plan (Departure Level) | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
640 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-01-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-01 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
641 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-02-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-02 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
642 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-03-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-03 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
643 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-04-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-04 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
644 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-05-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-05 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
645 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-06-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-06 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
646 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-07-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-07 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
647 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-08-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-08 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
648 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-09-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-09 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
649 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-10-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-10 | 2025-05-22 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
650 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-11-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-11 | 2025-05-22 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
651 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-12-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-12 | 2025-06-02 | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
652 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-13-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-13 |  | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
653 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-14-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-14 |  | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
654 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | MCK | SD | 0 | 1300403-ATS-B01-FF-15-ICT-MCK-SD-00 | First Floor Master Clock System Plan Part-15 |  | 6 | --- | 0 | 45805 | ATLS-004-SD-ICT-00021-R00 | Code 2 | 03 Jun 25 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 |  | ATLS-004-SD-ICT-00021-R00 | 2025-05-28 | ATV-1300000403-SDS-ICT-00014-R00 | 2025-06-01 | ATV-1300000403-SDS-ICT-00014-R00 | Code 2 | 2025-06-03 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
655 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-MCK-SD-00 | Mezzanine Floor Master Clock Overall System Plan | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
656 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 1 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-01-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-01 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
657 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-02 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
658 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-03 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
659 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 4 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-04-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-04 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
660 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 5 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-05-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-05 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
661 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-06 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
662 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-07 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
663 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 8 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-08-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-08 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
664 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 9 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-09-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-09 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
665 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-10 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
666 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-11 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
667 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-12 | 2025-06-02 | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
668 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-13-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-13 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
669 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-14-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-14 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
670 | ICT | MASTER CLOCK SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | MCK | SD | 0 | 1300403-ATS-B01-MZ-15-ICT-MCK-SD-00 | Mezzanine Floor Master Clock System Plan Part-15 |  | 3 | --- | 0 | 45806 | ATLS-004-SD-ICT-00022-R00 | Code 2 | 1 Jun 2025 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 |  | ATLS-004-SD-ICT-00022-R00 | 2025-05-29 | ATV-1300000403-SDS-ICT-00012-R00 | 2025-05-31 | ATV-1300000403-SDS-ICT-00012-R00 | Code 2 | 2025-06-01 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
671 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-00-ICT-ACS-SD-00 | Terminal Basement Floor Access Control Overall System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
672 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-01-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
673 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-02-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
674 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-03-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
675 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-04-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
676 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-05-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-05 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
677 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-06-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-06 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
678 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-07-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
679 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-08-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-08 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
680 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-09-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-09 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
681 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-10-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-10 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
682 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-11-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-11 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
683 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | ACS | SD | 0 | 1300403-ATS-B01-BF-12-ICT-ACS-SD-00 | Terminal Basement Floor Access Control System Plan Part-12 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
684 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-00-ICT-ACS-SD-00 | Ground Floor Access Control Overall System Plan (Arrival Level) | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
685 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-01-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
686 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-02-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
687 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-03-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
688 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-04-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
689 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-05-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-05 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
690 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-06-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-06 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
691 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-07-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
692 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-08-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-08 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
693 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-09-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-09 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
694 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-10-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-10 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
695 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-11-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-11 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
696 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-12-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-12 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
697 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-13-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-13 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
698 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-14-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-14 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
699 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | ACS | SD | 0 | 1300403-ATS-B01-GF-15-ICT-ACS-SD-00 | Ground Floor Access Control System Plan Part-15 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
700 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-00-ICT-ACS-SD-00 | First Floor Access Control Overall System Plan(Departure Level) | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
701 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-01-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
702 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-02-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
703 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-03-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
704 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-04-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
705 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-05-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-05 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
706 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-06-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-06 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
707 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-07-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
708 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-08-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-08 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
709 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-09-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-09 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
710 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-10-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-10 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
711 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-11-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-11 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
712 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-12-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-12 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
713 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-13-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-13 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
714 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-14-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-14 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
715 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | ACS | SD | 0 | 1300403-ATS-B01-FF-15-ICT-ACS-SD-00 | First Floor Access Control System Plan Part-15 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
716 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | ACS | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-ACS-SD-00 | Mezzanine Floor Access Control Overall System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
717 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | ACS | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
718 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | ACS | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
719 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | ACS | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-06 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
720 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | ACS | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
721 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | ACS | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-10 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
722 | ICT | ACCESS CONTROL SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | ACS | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-ACS-SD-00 | Mezzanine Floor Access Control System Plan Part-11 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
723 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-00-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance Overall System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
724 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-01-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
725 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-02-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
726 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-03-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
727 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-04-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
728 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-05-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-05 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
729 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-06-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-06 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
730 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-07-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
731 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-08-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-08 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
732 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-09-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-09 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
733 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-10-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-10 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
734 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-11-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-11 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
735 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | SEC | SD | 0 | 1300403-ATS-B01-BF-12-ICT-SEC-SD-00 | Terminal Basement Floor Video Survelliance System Plan Part-12 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
736 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-00-ICT-SEC-SD-00 | Ground Floor Video Survelliance Overall System Plan (Arrival Level) | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
737 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-01-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
738 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-02-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
739 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-03-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
740 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-04-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
741 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-05-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-05 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
742 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-06-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-06 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
743 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-07-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
744 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-08-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-08 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
745 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-09-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-09 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
746 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-10-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-10 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
747 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-11-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-11 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
748 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-12-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-12 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
749 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-13-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-13 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
750 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-14-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-14 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
751 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | SEC | SD | 0 | 1300403-ATS-B01-GF-15-ICT-SEC-SD-00 | Ground Floor Video Survelliance System Plan Part-15 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
752 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | 00 | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B01-00-00-ICT-SEC-SD-00 | Local Area Video Survelliance System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
753 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-00-ICT-SEC-SD-00 | First Floor Video Survelliance Overall System Plan (Departure Level) | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
754 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-01-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-01 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
755 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-02-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
756 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-03-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
757 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-04-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-04 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
758 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-05-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-05 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
759 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-06-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-06 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
760 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-07-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
761 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-08-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-08 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
762 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-09-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-09 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
763 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-10-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-10 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
764 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-11-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-11 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
765 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-12-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-12 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
766 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-13-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-13 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
767 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-14-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-14 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
768 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | SEC | SD | 0 | 1300403-ATS-B01-FF-15-ICT-SEC-SD-00 | First Floor Video Survelliance System Plan Part-15 | 2025-05-12 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
769 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance Overall System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
770 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
771 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
772 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-06 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
773 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
774 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-10 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
775 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-11 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
776 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-12 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
777 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-13-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-13 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
778 | ICT | VIDEO SURVELLIANCE SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | SEC | SD | 0 | 1300403-ATS-B01-MZ-15-ICT-SEC-SD-00 | Mezzanine Floor Video Survelliance System Plan Part-15 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
779 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-00-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication Overall System Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
780 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-01-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
781 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-02-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
782 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-03-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
783 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-06-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-06 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
784 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-07-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
785 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-09-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-09 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
786 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-10-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-10 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
787 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-11-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-11 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
788 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | WAP | SD | 0 | 1300403-ATS-B01-BF-12-ICT-WAP-SD-00 | Terminal Basement Wireless Lan Communication System Plan Part-12 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
789 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-00-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication Overall System Plan (Arrival Level) | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
790 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-01-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
791 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-02-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
792 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-03-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
793 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-04-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-04 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
794 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-06-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-06 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
795 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-07-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
796 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-08-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-08 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
797 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-09-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-09 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
798 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-10-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-10 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
799 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-11-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-11 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
800 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-13-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-13 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
801 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-14-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-14 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
802 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | WAP | SD | 0 | 1300403-ATS-B01-GF-15-ICT-WAP-SD-00 | Ground Floor Wireless Lan Communication System Plan Part-15 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
803 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | 00 | 0 | ICT | WAP | SD | 0 | 1300403-ATS-B01-00-00-ICT-WAP-SD-00 | Locker Area Wireless Lan Communication System Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
804 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-00-ICT-WAP-SD-00 | First Floor Wireless Lan Communication Overall System Plan (Departure Level) | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
805 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-01-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
806 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-02-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
807 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-03-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
808 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-04-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-04 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
809 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-05-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-05 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
810 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-06-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-06 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
811 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-07-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
812 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-08-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-08 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
813 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-09-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-09 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
814 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-10-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-10 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
815 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-11-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-11 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
816 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-12-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-12 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
817 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-13-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-13 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
818 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-14-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-14 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
819 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | WAP | SD | 0 | 1300403-ATS-B01-FF-15-ICT-WAP-SD-00 | First Floor Wireless Lan Communication System Plan Part-15 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
820 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | WAP | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication Overall System Plan | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
821 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | WAP | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication System Plan Part-06 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
822 | ICT | WIRELESS LAN COMMUNICATION SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | WAP | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-WAP-SD-00 | Mezzanine Floor Wireless Lan Communication System Plan Part-07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
823 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-00-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm Overall System Plan (Arrival Level) | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
824 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-08-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-08 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
825 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-10-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-10 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
826 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-11-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-11 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
827 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-12-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-12 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
828 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-13-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-13 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
829 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-14-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-14 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
830 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | ECS | SD | 0 | 1300403-ATS-B01-GF-15-ICT-ECS-SD-00 | Ground Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-15 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
831 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-00-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm Overall System Plan (Arrival Level) | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
832 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-06-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-06 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
833 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-07-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-07 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
834 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-09-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-09 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
835 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-10-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-10 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
836 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-11-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-11 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
837 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-12-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-12 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
838 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-13-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-13 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
839 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-14-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-14 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
840 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | ECS | SD | 0 | 1300403-ATS-B01-FF-15-ICT-ECS-SD-00 | First Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-15 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
841 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | ECS | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-ECS-SD-00 | Mezzanine Floor Emergency Communication System & Disabled Toilet Alarm Overall System Plan | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
842 | ICT | EMERGENCY COMMUNICATION & DISABLED TOILET ALARM SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | ECS | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-ECS-SD-00 | Mezzanine Floor Emergency Communication System & Disabled Toilet Alarm System Plan Part-06 | 2025-05-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
843 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-00-ICT-DAT-SD-00 | Terminal Basement Data Network Overall System Plan | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
844 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-01-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-01 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
845 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-02-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-02 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
846 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-03-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-03 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
847 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-04-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-04 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
848 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-05-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-05 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
849 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-06-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-06 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
850 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-07-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-07 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
851 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-08-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-08 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
852 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-09-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-09 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
853 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-10-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-10 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
854 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-11-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-11 | 2025-05-18 | 36 |  | 0 | 45781 | ATLS-004-SD-ICT-00017-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00017-R00 | 2025-05-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
855 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | DAT | SD | 0 | 1300403-ATS-B01-BF-12-ICT-DAT-SD-00 | Terminal Basement Data Network System Plan Part-12 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
856 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-00-ICT-DAT-SD-00 | Ground Floor Data Network Overall System Plan (Arrival Level) | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
857 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-01-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-01 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
858 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-02-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-02 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
859 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-03-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-03 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
860 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-04-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-04 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
861 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-05-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-05 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
862 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-06-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-06 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
863 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-07-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-07 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
864 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-08-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-08 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
865 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-09-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-09 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
866 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-10-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-10 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
867 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-11-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-11 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
868 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-12-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-12 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
869 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-13-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-13 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
870 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-14-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-14 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
871 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | DAT | SD | 0 | 1300403-ATS-B01-GF-15-ICT-DAT-SD-00 | Ground Floor Data Network System Plan Part-15 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
872 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | 00 | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B01-00-00-ICT-DAT-SD-00 | Locker Area Data Network System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
873 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-00-ICT-DAT-SD-00 | First Floor Data Network Overall System Plan (Departure Level) | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
874 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-01-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-01 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
875 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-02-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-02 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
876 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-03-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-03 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
877 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-04-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-04 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
878 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-05-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-05 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
879 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-06-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-06 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
880 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-07-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-07 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
881 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-08-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-08 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
882 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-09-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-09 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
883 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-10-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-10 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
884 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-11-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-11 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
885 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-12-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-12 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
886 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-13-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-13 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
887 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-14-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-14 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
888 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | DAT | SD | 0 | 1300403-ATS-B01-FF-15-ICT-DAT-SD-00 | First Floor Data Network System Plan Part-15 | 2025-05-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
889 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | DAT | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-DAT-SD-00 | Mezzanine Floor Data Network Overall System Plan | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
890 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | DAT | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-02 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
891 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | DAT | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-03 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
892 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | DAT | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-06 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
893 | ICT | DATA NETWORK SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | DAT | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-DAT-SD-00 | Mezzanine Floor Data Network System Plan Part-07 | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
894 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-00-ICT-SIG-SD-00 | Ground Floor Digital Signage Overall Layout Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
895 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-01-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-01 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
896 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-02-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-02 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
897 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-03-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-03 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
898 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-04-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-04 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
899 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-05-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-05 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
900 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-06-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-06 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
901 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-07-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-07 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
902 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-08-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-08 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
903 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-09-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-09 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
904 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-10-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-10 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
905 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-11-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-11 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
906 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-12-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-12 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
907 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-13-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-13 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
908 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-14-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-14 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
909 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | SIG | SD | 0 | 1300403-ATS-B01-GF-15-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-15 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
910 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-00-ICT-SIG-SD-00 | First Floor Digital Signage Overall Layout Plan | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
911 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-04-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-04 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
912 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-05-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-05 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
913 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-06-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-06 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
914 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-07-ICT-SIG-SD-00 | Firstfloor Digital Signage Layout Plan Part-07 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
915 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-08-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-08 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
916 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-09-ICT-SIG-SD-00 | Firstfloor Digital Signage Layout Plan Part-09 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
917 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-10-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-10 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
918 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-11-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-11 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
919 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-12-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-12 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
920 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-13-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-13 | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
921 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-14-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-14 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
922 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | SIG | SD | 0 | 1300403-ATS-B01-FF-15-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-15 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
923 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | SIG | SD | 0 | 1300403-ATS-B02-GF-00-ICT-SIG-SD-00 | Ground Floor Digital Signage Overall Layout Plan | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
924 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 6 | ICT | SIG | SD | 0 | 1300403-ATS-B02-GF-06-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-06 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
925 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 10 | ICT | SIG | SD | 0 | 1300403-ATS-B02-GF-10-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-10 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
926 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | GF | 14 | ICT | SIG | SD | 0 | 1300403-ATS-B02-GF-14-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-14 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
927 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | SIG | SD | 0 | 1300403-ATS-B02-FF-00-ICT-SIG-SD-00 | First Floor Digital Signage Overall Layout Plan | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
928 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 6 | ICT | SIG | SD | 0 | 1300403-ATS-B02-FF-06-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-06 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
929 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 7 | ICT | SIG | SD | 0 | 1300403-ATS-B02-FF-07-ICT-SIG-SD-00 | First Floor Digital Signage Layout Plan Part-07 | 2025-05-24 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
930 | ICT | SIGNAGE SYSTEM | 1300403 | ATS | B02 | FF | 11 | ICT | SIG | SD | 0 | 1300403-ATS-B02-FF-11-ICT-SIG-SD-00 | Ground Floor Digital Signage Layout Plan Part-11 | 2025-05-22 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
931 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 0 | 1300403-ATS-B0X-00-00-ICT-STL-SD-00 | Master Site Plan Telecommunication Works | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
932 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 1 | 1300403-ATS-B0X-00-00-ICT-STL-SD-01 | Partial Site Telecommunication Plan (Part1) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
933 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 2 | 1300403-ATS-B0X-00-00-ICT-STL-SD-02 | Partial Site Telecommunication Plan (Part2) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
934 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 3 | 1300403-ATS-B0X-00-00-ICT-STL-SD-03 | Partial Site Telecommunication Plan (Part3) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
935 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 4 | 1300403-ATS-B0X-00-00-ICT-STL-SD-04 | Partial Site Telecommunication Plan (Part4) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
936 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 5 | 1300403-ATS-B0X-00-00-ICT-STL-SD-05 | Partial Site Telecommunication Plan (Part5) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
937 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 6 | 1300403-ATS-B0X-00-00-ICT-STL-SD-06 | Partial Site Telecommunication Plan (Part6) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
938 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 7 | 1300403-ATS-B0X-00-00-ICT-STL-SD-07 | Partial Site Telecommunication Plan (Part7) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
939 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 8 | 1300403-ATS-B0X-00-00-ICT-STL-SD-08 | Partial Site Telecommunication Plan (Part8) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
940 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 9 | 1300403-ATS-B0X-00-00-ICT-STL-SD-09 | Partial Site Telecommunication Plan (Part9) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
941 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 10 | 1300403-ATS-B0X-00-00-ICT-STL-SD-10 | Partial Site Telecommunication Plan (Part10) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
942 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 11 | 1300403-ATS-B0X-00-00-ICT-STL-SD-11 | Partial Site Telecommunication Plan (Part11) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
943 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 12 | 1300403-ATS-B0X-00-00-ICT-STL-SD-12 | Partial Site Telecommunication Plan (Part12) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
944 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 13 | 1300403-ATS-B0X-00-00-ICT-STL-SD-13 | Partial Site Telecommunication Plan (Part13) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
945 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 14 | 1300403-ATS-B0X-00-00-ICT-STL-SD-14 | Partial Site Telecommunication Plan (Part14) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
946 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 15 | 1300403-ATS-B0X-00-00-ICT-STL-SD-15 | Partial Site Telecommunication Plan (Part15) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
947 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 16 | 1300403-ATS-B0X-00-00-ICT-STL-SD-16 | Partial Site Telecommunication Plan (Part16) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
948 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 17 | 1300403-ATS-B0X-00-00-ICT-STL-SD-17 | Partial Site Telecommunication Plan (Part17) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
949 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 18 | 1300403-ATS-B0X-00-00-ICT-STL-SD-18 | Partial Site Telecommunication Plan (Part18) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
950 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 19 | 1300403-ATS-B0X-00-00-ICT-STL-SD-19 | Partial Site Telecommunication Plan (Part19) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
951 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 20 | 1300403-ATS-B0X-00-00-ICT-STL-SD-20 | Partial Site Telecommunication Plan (Part20) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
952 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 21 | 1300403-ATS-B0X-00-00-ICT-STL-SD-21 | Partial Site Telecommunication Plan (Part21) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
953 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 22 | 1300403-ATS-B0X-00-00-ICT-STL-SD-22 | Partial Site Telecommunication Plan (Part22) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
954 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 23 | 1300403-ATS-B0X-00-00-ICT-STL-SD-23 | Partial Site Telecommunication Plan (Part23) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
955 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 24 | 1300403-ATS-B0X-00-00-ICT-STL-SD-24 | Partial Site Telecommunication Plan (Part24) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
956 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 25 | 1300403-ATS-B0X-00-00-ICT-STL-SD-25 | Partial Site Telecommunication Plan (Part25) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
957 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 26 | 1300403-ATS-B0X-00-00-ICT-STL-SD-26 | Partial Site Telecommunication Plan (Part26) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
958 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 27 | 1300403-ATS-B0X-00-00-ICT-STL-SD-27 | Partial Site Telecommunication Plan (Part27) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
959 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 28 | 1300403-ATS-B0X-00-00-ICT-STL-SD-28 | Partial Site Telecommunication Plan (Part28) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
960 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 29 | 1300403-ATS-B0X-00-00-ICT-STL-SD-29 | Partial Site Telecommunication Plan (Part29) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
961 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 30 | 1300403-ATS-B0X-00-00-ICT-STL-SD-30 | Partial Site Telecommunication Plan (Part30) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
962 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 31 | 1300403-ATS-B0X-00-00-ICT-STL-SD-31 | Partial Site Telecommunication Plan (Part31) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
963 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 32 | 1300403-ATS-B0X-00-00-ICT-STL-SD-32 | Site Plan Telecommunication Works ( For Departure Level ) | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
964 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 33 | 1300403-ATS-B0X-00-00-ICT-STL-SD-33 | Site Plan Telecommunication Works ( For Departure Level ) Part 01 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
965 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 34 | 1300403-ATS-B0X-00-00-ICT-STL-SD-34 | Site Plan Telecommunication Works ( For Departure Level ) Part 02 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
966 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 35 | 1300403-ATS-B0X-00-00-ICT-STL-SD-35 | Site Plan Telecommunication Works ( For Departure Level ) Part 03 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
967 | ICT | SITE TELECOMMUNICATION SYSTEM | 1300403 | ATS | B0X | 00 | 0 | ICT | STL | SD | 36 | 1300403-ATS-B0X-00-00-ICT-STL-SD-36 | Site Plan Telecommunication Works ( For Departure Level ) Part 04 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
968 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 0 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-00-ICT-IPT-SD-00 | Ground Floor Iptv System Overall Plan (Arrival Level) | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
969 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 1 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-01-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 01 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
970 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 2 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-02-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 02 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
971 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 3 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-03-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 03 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
972 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 4 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-04-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 04 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
973 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 5 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-05-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 05 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
974 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 6 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-06-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 06 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
975 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 7 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-07-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 07 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
976 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 8 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-08-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 08 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
977 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 9 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-09-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 09 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
978 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 10 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-10-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 10 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
979 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 11 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-11-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 11 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
980 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 12 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-12-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 12 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
981 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 13 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-13-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 13 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
982 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 14 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-14-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 14 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
983 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | GF | 15 | ICT | IPT | SD | 0 | 1300403-ATS-B01-GF-15-ICT-IPT-SD-00 | Ground Floor Iptv System Plan (Arrival Level) Part 15 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00032-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00032-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00019-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
984 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 0 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-00-ICT-IPT-SD-00 | First Floor Iptv System Overall Plan (Departure Level) | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
985 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 1 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-01-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 01 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
986 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 2 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-02-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 02 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
987 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 3 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-03-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 03 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
988 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 4 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-04-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 04 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
989 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 5 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-05-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 05 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
990 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 6 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-06-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 06 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
991 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 7 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-07-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 07 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
992 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 8 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-08-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 08 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
993 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 9 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-09-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 09 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
994 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 10 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-10-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 10 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
995 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 11 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-11-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 11 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
996 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 12 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-12-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 12 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
997 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 13 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-13-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 13 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
998 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 14 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-14-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 14 | 2025-05-25 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
999 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | FF | 15 | ICT | IPT | SD | 0 | 1300403-ATS-B01-FF-15-ICT-IPT-SD-00 | First Floor Iptv System Plan (Departure Level) Part 15 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00031-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00031-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00018-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1000 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 0 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-00-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Overall Plan | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1001 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 1 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-01-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 01 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1002 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 2 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-02-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 02 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1003 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 3 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-03-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 03 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1004 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 4 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-04-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 04 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1005 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 5 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-05-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 05 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1006 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 6 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-06-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 06 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1007 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 7 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-07-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 07 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1008 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 8 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-08-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 08 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1009 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 9 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-09-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 09 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1010 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 10 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-10-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 10 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1011 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 11 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-11-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 11 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1012 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 12 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-12-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 12 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1013 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 13 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-13-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 13 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1014 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 14 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-14-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 14 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1015 | ICT | IPTV SYSTEM | 1300403 | ATS | B01 | MZ | 15 | ICT | IPT | SD | 0 | 1300403-ATS-B01-MZ-15-ICT-IPT-SD-00 | Mezzanine Floor Iptv System Plan Part 15 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00034-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00034-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00020-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1016 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 0 | ICT | IPT | SD | 0 | 1300403-ATS-B02-GF-00-ICT-IPT-SD-00 | Ground Floor Iptv System Overall Plan | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1017 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 1 | ICT | IPT | SD | 0 | 1300403-ATS-B02-GF-01-ICT-IPT-SD-00 | Ground Floor Iptv System Plan Part 01 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1018 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 2 | ICT | IPT | SD | 0 | 1300403-ATS-B02-GF-02-ICT-IPT-SD-00 | Ground Floor Iptv System Plan Part 02 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1019 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | GF | 3 | ICT | IPT | SD | 0 | 1300403-ATS-B02-GF-03-ICT-IPT-SD-00 | Ground Floor Iptv System Plan Part 03 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1020 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 0 | ICT | IPT | SD | 0 | 1300403-ATS-B02-FF-00-ICT-IPT-SD-00 | First Floor Iptv System Overall Plan | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1021 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 1 | ICT | IPT | SD | 0 | 1300403-ATS-B02-FF-01-ICT-IPT-SD-00 | First Floor Iptv System Plan Part 01 | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1022 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 2 | ICT | IPT | SD | 0 | 1300403-ATS-B02-FF-02-ICT-IPT-SD-00 | First Floor Iptv System Plan Part 02 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1023 | ICT | IPTV SYSTEM | 1300403 | ATS | B02 | FF | 3 | ICT | IPT | SD | 0 | 1300403-ATS-B02-FF-03-ICT-IPT-SD-00 | First Floor Iptv System Plan Part 03 |  | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00033-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00033-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00021-R00 | 2025-06-02 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1024 | ICT | IPTV SYSTEM | 1300403 | ATS | B06 | 00 | 0 | ICT | IPT | SD | 0 | 1300403-ATS-B06-00-00-ICT-IPT-SD-00 | Ground Floor Iptv System Plan | 2025-06-02 | 5 |  | 0 | 45812 | ATLS-004-SD-ICT-00035-R00 | UR (ATJV) | --- |  | UR (ATJV) |  | ATLS-004-SD-ICT-00035-R00 | 2025-06-04 |  |  |  | UR (ATJV) |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1025 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 0 | 1300403-ATS-B01-00-00-ICT-SCH-SD-00 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1026 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 1 | 1300403-ATS-B01-00-00-ICT-SCH-SD-01 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1027 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 2 | 1300403-ATS-B01-00-00-ICT-SCH-SD-02 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1028 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 3 | 1300403-ATS-B01-00-00-ICT-SCH-SD-03 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1029 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 4 | 1300403-ATS-B01-00-00-ICT-SCH-SD-04 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1030 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 5 | 1300403-ATS-B01-00-00-ICT-SCH-SD-05 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1031 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 6 | 1300403-ATS-B01-00-00-ICT-SCH-SD-06 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1032 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 7 | 1300403-ATS-B01-00-00-ICT-SCH-SD-07 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1033 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 8 | 1300403-ATS-B01-00-00-ICT-SCH-SD-08 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1034 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 9 | 1300403-ATS-B01-00-00-ICT-SCH-SD-09 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1035 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 10 | 1300403-ATS-B01-00-00-ICT-SCH-SD-10 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1036 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 11 | 1300403-ATS-B01-00-00-ICT-SCH-SD-11 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1037 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 12 | 1300403-ATS-B01-00-00-ICT-SCH-SD-12 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1038 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 13 | 1300403-ATS-B01-00-00-ICT-SCH-SD-13 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1039 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 14 | 1300403-ATS-B01-00-00-ICT-SCH-SD-14 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1040 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 15 | 1300403-ATS-B01-00-00-ICT-SCH-SD-15 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1041 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 16 | 1300403-ATS-B01-00-00-ICT-SCH-SD-16 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1042 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 17 | 1300403-ATS-B01-00-00-ICT-SCH-SD-17 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1043 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 18 | 1300403-ATS-B01-00-00-ICT-SCH-SD-18 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1044 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B01 | 00 | 0 | ICT | SCH | SD | 19 | 1300403-ATS-B01-00-00-ICT-SCH-SD-19 | Security System Acs And Cctv Schedules | 2025-05-26 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1045 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 0 | 1300403-ATS-B02-00-00-ICT-SCH-SD-00 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1046 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 1 | 1300403-ATS-B02-00-00-ICT-SCH-SD-01 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1047 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 2 | 1300403-ATS-B02-00-00-ICT-SCH-SD-02 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1048 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 3 | 1300403-ATS-B02-00-00-ICT-SCH-SD-03 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1049 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 4 | 1300403-ATS-B02-00-00-ICT-SCH-SD-04 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1050 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 5 | 1300403-ATS-B02-00-00-ICT-SCH-SD-05 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1051 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 6 | 1300403-ATS-B02-00-00-ICT-SCH-SD-06 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1052 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 7 | 1300403-ATS-B02-00-00-ICT-SCH-SD-07 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1053 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 8 | 1300403-ATS-B02-00-00-ICT-SCH-SD-08 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1054 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 9 | 1300403-ATS-B02-00-00-ICT-SCH-SD-09 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1055 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 10 | 1300403-ATS-B02-00-00-ICT-SCH-SD-10 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1056 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 11 | 1300403-ATS-B02-00-00-ICT-SCH-SD-11 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1057 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 12 | 1300403-ATS-B02-00-00-ICT-SCH-SD-12 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1058 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 13 | 1300403-ATS-B02-00-00-ICT-SCH-SD-13 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1059 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B02 | 00 | 0 | ICT | SCH | SD | 14 | 1300403-ATS-B02-00-00-ICT-SCH-SD-14 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1060 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B03 | 00 | 0 | ICT | SCH | SD | 0 | 1300403-ATS-B03-00-00-ICT-SCH-SD-00 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1061 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B03 | 00 | 0 | ICT | SCH | SD | 1 | 1300403-ATS-B03-00-00-ICT-SCH-SD-01 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1062 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B03 | 00 | 0 | ICT | SCH | SD | 2 | 1300403-ATS-B03-00-00-ICT-SCH-SD-02 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1063 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B03 | 00 | 0 | ICT | SCH | SD | 3 | 1300403-ATS-B03-00-00-ICT-SCH-SD-03 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1064 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B03 | 00 | 0 | ICT | SCH | SD | 4 | 1300403-ATS-B03-00-00-ICT-SCH-SD-04 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1065 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B03 | 00 | 0 | ICT | SCH | SD | 5 | 1300403-ATS-B03-00-00-ICT-SCH-SD-05 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1066 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B04 | 00 | 0 | ICT | SCH | SD | 0 | 1300403-ATS-B04-00-00-ICT-SCH-SD-00 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1067 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B04 | 00 | 0 | ICT | SCH | SD | 1 | 1300403-ATS-B04-00-00-ICT-SCH-SD-01 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1068 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B04 | 00 | 0 | ICT | SCH | SD | 2 | 1300403-ATS-B04-00-00-ICT-SCH-SD-02 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1069 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B04 | 00 | 0 | ICT | SCH | SD | 3 | 1300403-ATS-B04-00-00-ICT-SCH-SD-03 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1070 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B05 | 00 | 0 | ICT | SCH | SD | 0 | 1300403-ATS-B05-00-00-ICT-SCH-SD-00 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1071 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B05 | 00 | 0 | ICT | SCH | SD | 1 | 1300403-ATS-B05-00-00-ICT-SCH-SD-01 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1072 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B05 | 00 | 0 | ICT | SCH | SD | 2 | 1300403-ATS-B05-00-00-ICT-SCH-SD-02 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1073 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B05 | 00 | 0 | ICT | SCH | SD | 3 | 1300403-ATS-B05-00-00-ICT-SCH-SD-03 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1074 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B06 | 00 | 0 | ICT | SCH | SD | 0 | 1300403-ATS-B06-00-00-ICT-SCH-SD-00 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1075 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B06 | 00 | 0 | ICT | SCH | SD | 1 | 1300403-ATS-B06-00-00-ICT-SCH-SD-01 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1076 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B06 | 00 | 0 | ICT | SCH | SD | 2 | 1300403-ATS-B06-00-00-ICT-SCH-SD-02 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1077 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B06 | 00 | 0 | ICT | SCH | SD | 3 | 1300403-ATS-B06-00-00-ICT-SCH-SD-03 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1078 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B07 | 00 | 0 | ICT | SCH | SD | 0 | 1300403-ATS-B07-00-00-ICT-SCH-SD-00 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1079 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B07 | 00 | 0 | ICT | SCH | SD | 1 | 1300403-ATS-B07-00-00-ICT-SCH-SD-01 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1080 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B07 | 00 | 0 | ICT | SCH | SD | 2 | 1300403-ATS-B07-00-00-ICT-SCH-SD-02 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1081 | ICT | SECURITY SYSTEM ACS AND CCTV SCHEDULES | 1300403 | ATS | B07 | 00 | 0 | ICT | SCH | SD | 3 | 1300403-ATS-B07-00-00-ICT-SCH-SD-03 | Security System Acs And Cctv Schedules | 2025-05-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1082 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 1 | 1300403-ATS-00-00-00-ICT-TYP-SD-01 | ACCESS CONTROL AC1 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1083 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 2 | 1300403-ATS-00-00-00-ICT-TYP-SD-02 | ACCESS CONTROL AC2 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1084 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 3 | 1300403-ATS-00-00-00-ICT-TYP-SD-03 | ACCESS CONTROL AC3 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1085 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 4 | 1300403-ATS-00-00-00-ICT-TYP-SD-04 | ACCESS CONTROL AC4 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1086 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 5 | 1300403-ATS-00-00-00-ICT-TYP-SD-05 | ACCESS CONTROL AC5 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1087 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 6 | 1300403-ATS-00-00-00-ICT-TYP-SD-06 | ACCESS CONTROL AC6 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1088 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 7 | 1300403-ATS-00-00-00-ICT-TYP-SD-07 | ACCESS CONTROL AC7 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1089 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 8 | 1300403-ATS-00-00-00-ICT-TYP-SD-08 | ACCESS CONTROL AC8 SLIDING DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1090 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 9 | 1300403-ATS-00-00-00-ICT-TYP-SD-09 | ACCESS CONTROL AC9 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1091 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 10 | 1300403-ATS-00-00-00-ICT-TYP-SD-10 | ACCESS CONTROL AC10 DOUBLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1092 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 11 | 1300403-ATS-00-00-00-ICT-TYP-SD-11 | ACCESS CONTROL AC11 SINGLE DOOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1093 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 12 | 1300403-ATS-00-00-00-ICT-TYP-SD-12 | ACCESS CONTROL AC12 SHUTTER INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1094 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 13 | 1300403-ATS-00-00-00-ICT-TYP-SD-13 | ACCESS CONTROL AC13 ELEVATOR INSTALLATION DETAIL | 2025-06-02 | 7 | --- | 0 | 45810 | ATLS-004-SD-ICT-00024-R00 | UR (DAR) | --- |  | UR (DAR) |  | ATLS-004-SD-ICT-00024-R00 | 2025-06-02 | ATV-1300000403-SDS-ICT-00025-R00 | 2025-06-03 |  | --- |  | UR (DAR) |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1095 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 14 | 1300403-ATS-00-00-00-ICT-TYP-SD-14 | ACCESS CONTROL SYSTEM SINGLE LINE DIAGRAM FOR BUILDING 05 | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1096 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 15 | 1300403-ATS-00-00-00-ICT-TYP-SD-15 | ACCESS CONTROL SYSTEM SINGLE LINE DIAGRAM FOR BUILDING 06 | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1097 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 16 | 1300403-ATS-00-00-00-ICT-TYP-SD-16 | ACCESS CONTROL SYSTEM SINGLE LINE DIAGRAM FOR BUILDING 07 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1098 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 17 | 1300403-ATS-00-00-00-ICT-TYP-SD-17 | INSTALLATION DETAIL FOR IPTV | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1099 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 18 | 1300403-ATS-00-00-00-ICT-TYP-SD-18 | INSTALLATION DETAIL FOR MASTER CLOCK | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1100 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 19 | 1300403-ATS-00-00-00-ICT-TYP-SD-19 | ICT RM -B0001BS-047-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1101 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 20 | 1300403-ATS-00-00-00-ICT-TYP-SD-20 | MMR -B0001BS-025-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1102 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 21 | 1300403-ATS-00-00-00-ICT-TYP-SD-21 | ICT RM -B0001BS-058-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1103 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 22 | 1300403-ATS-00-00-00-ICT-TYP-SD-22 | ICT RM / SERVIES CORRIDOR -B0001BS-105/155-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1104 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 23 | 1300403-ATS-00-00-00-ICT-TYP-SD-23 | MMR -B0001BS-110-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1105 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 24 | 1300403-ATS-00-00-00-ICT-TYP-SD-24 | MTR-B0001BS-140-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1106 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 25 | 1300403-ATS-00-00-00-ICT-TYP-SD-25 | ICT RM -B0001BS-116-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1107 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 26 | 1300403-ATS-00-00-00-ICT-TYP-SD-26 | ICT RM-B0001GR-190-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1108 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 27 | 1300403-ATS-00-00-00-ICT-TYP-SD-27 | DAS/TETRA RM-B0001GR-450-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1109 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 28 | 1300403-ATS-00-00-00-ICT-TYP-SD-28 | ICT RM-B0001GR-172-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1110 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 29 | 1300403-ATS-00-00-00-ICT-TYP-SD-29 | SERVER RM -B0001GR-361-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1111 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 30 | 1300403-ATS-00-00-00-ICT-TYP-SD-30 | ICT RM -B0001GR-363-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1112 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 31 | 1300403-ATS-00-00-00-ICT-TYP-SD-31 | ICT RM -B0001GR-353-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1113 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 32 | 1300403-ATS-00-00-00-ICT-TYP-SD-32 | SERVER RM -B0001GR-218-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1114 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 33 | 1300403-ATS-00-00-00-ICT-TYP-SD-33 | ICT RM-B0001GR-216-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1115 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 34 | 1300403-ATS-00-00-00-ICT-TYP-SD-34 | ICT RM-B0001GR-136-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1116 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 35 | 1300403-ATS-00-00-00-ICT-TYP-SD-35 | ICT RM-B0001GR-155-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1117 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 36 | 1300403-ATS-00-00-00-ICT-TYP-SD-36 | ICT RM-B0001GR-097-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1118 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 37 | 1300403-ATS-00-00-00-ICT-TYP-SD-37 | ICT RM-B0001GR-028-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1119 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 38 | 1300403-ATS-00-00-00-ICT-TYP-SD-38 | ICT RM-B0001GR-014-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1120 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 39 | 1300403-ATS-00-00-00-ICT-TYP-SD-39 | ELEC RM-B0001GR-233-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1121 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 40 | 1300403-ATS-00-00-00-ICT-TYP-SD-40 | ICT RM -B0001GR-295-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1122 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 41 | 1300403-ATS-00-00-00-ICT-TYP-SD-41 | ICT RM-B0001 01-262-264-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1123 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 42 | 1300403-ATS-00-00-00-ICT-TYP-SD-42 | ICT RM-B0001 01-106-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1124 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 43 | 1300403-ATS-00-00-00-ICT-TYP-SD-43 | ICT RM-B0001 01-205-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1125 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 44 | 1300403-ATS-00-00-00-ICT-TYP-SD-44 | ICT RM-B0001 01-286-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1126 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 45 | 1300403-ATS-00-00-00-ICT-TYP-SD-45 | ICT RM-B0001 01-130-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1127 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 46 | 1300403-ATS-00-00-00-ICT-TYP-SD-46 | ICT RM-B000 1MZ-009-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1128 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 47 | 1300403-ATS-00-00-00-ICT-TYP-SD-47 | ICT RM-B000 1MZ-049-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1129 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 48 | 1300403-ATS-00-00-00-ICT-TYP-SD-48 | ICT RM-B000 1MZ-100-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1130 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 49 | 1300403-ATS-00-00-00-ICT-TYP-SD-49 | ICT RM-B000 1MZ-123-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1131 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 50 | 1300403-ATS-00-00-00-ICT-TYP-SD-50 | LC CLOSET -B0002-GR-108-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1132 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 51 | 1300403-ATS-00-00-00-ICT-TYP-SD-51 | ICT RM-B0002-GR-030-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1133 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 52 | 1300403-ATS-00-00-00-ICT-TYP-SD-52 | TELECOM RM-B0002-GR-025-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1134 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 53 | 1300403-ATS-00-00-00-ICT-TYP-SD-53 | ICT RM-B0002-01-021-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1135 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 54 | 1300403-ATS-00-00-00-ICT-TYP-SD-54 | LC ROOM-B0002-01-002-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1136 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 55 | 1300403-ATS-00-00-00-ICT-TYP-SD-55 | LC ROOM-B0003 BS-007-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1137 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 56 | 1300403-ATS-00-00-00-ICT-TYP-SD-56 | COMM.CLOSET-B0003 GR-002-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1138 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 57 | 1300403-ATS-00-00-00-ICT-TYP-SD-57 | COMM. ROOM-B0004 BS-011-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1139 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 58 | 1300403-ATS-00-00-00-ICT-TYP-SD-58 | COMM. ROOM-B0004 BS-012-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1140 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 59 | 1300403-ATS-00-00-00-ICT-TYP-SD-59 | COMM. ROOM-B0004 GD-010-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1141 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 60 | 1300403-ATS-00-00-00-ICT-TYP-SD-60 | COMM. ROOM-B0004 GD-009-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1142 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 61 | 1300403-ATS-00-00-00-ICT-TYP-SD-61 | COMM.ROOM-B0005 BS-032-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1143 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 62 | 1300403-ATS-00-00-00-ICT-TYP-SD-62 | COMM.ROOM-B0005 BS-026-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1144 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 63 | 1300403-ATS-00-00-00-ICT-TYP-SD-63 | TELEPHONE EQUIPMENT-B0005 BS-004-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1145 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 64 | 1300403-ATS-00-00-00-ICT-TYP-SD-64 | ICT RM-B0006 GR-004-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1146 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 65 | 1300403-ATS-00-00-00-ICT-TYP-SD-65 | COMM. ROOM-B0007-GR-006-SCR ROOM DETAILS AND RACK LAYOUT | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1147 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 66 | 1300403-ATS-00-00-00-ICT-TYP-SD-66 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1148 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 67 | 1300403-ATS-00-00-00-ICT-TYP-SD-67 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1149 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 68 | 1300403-ATS-00-00-00-ICT-TYP-SD-68 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1150 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 69 | 1300403-ATS-00-00-00-ICT-TYP-SD-69 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1151 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 70 | 1300403-ATS-00-00-00-ICT-TYP-SD-70 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1152 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 71 | 1300403-ATS-00-00-00-ICT-TYP-SD-71 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1153 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 72 | 1300403-ATS-00-00-00-ICT-TYP-SD-72 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1154 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 73 | 1300403-ATS-00-00-00-ICT-TYP-SD-73 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1155 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 74 | 1300403-ATS-00-00-00-ICT-TYP-SD-74 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1156 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 75 | 1300403-ATS-00-00-00-ICT-TYP-SD-75 | Typical Drawings | 2025-06-11 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1157 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 76 | 1300403-ATS-00-00-00-ICT-TYP-SD-76 | Typical Drawings | 2025-06-16 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1158 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 77 | 1300403-ATS-00-00-00-ICT-TYP-SD-77 | Typical Drawings | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1159 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 78 | 1300403-ATS-00-00-00-ICT-TYP-SD-78 | Typical Drawings | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1160 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 79 | 1300403-ATS-00-00-00-ICT-TYP-SD-79 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1161 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 80 | 1300403-ATS-00-00-00-ICT-TYP-SD-80 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1162 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 81 | 1300403-ATS-00-00-00-ICT-TYP-SD-81 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1163 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 82 | 1300403-ATS-00-00-00-ICT-TYP-SD-82 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1164 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 83 | 1300403-ATS-00-00-00-ICT-TYP-SD-83 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1165 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 84 | 1300403-ATS-00-00-00-ICT-TYP-SD-84 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1166 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 85 | 1300403-ATS-00-00-00-ICT-TYP-SD-85 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1167 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 86 | 1300403-ATS-00-00-00-ICT-TYP-SD-86 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1168 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 87 | 1300403-ATS-00-00-00-ICT-TYP-SD-87 | Typical Drawings | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1169 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 88 | 1300403-ATS-00-00-00-ICT-TYP-SD-88 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1170 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 89 | 1300403-ATS-00-00-00-ICT-TYP-SD-89 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1171 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 90 | 1300403-ATS-00-00-00-ICT-TYP-SD-90 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1172 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 91 | 1300403-ATS-00-00-00-ICT-TYP-SD-91 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1173 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 92 | 1300403-ATS-00-00-00-ICT-TYP-SD-92 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1174 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 93 | 1300403-ATS-00-00-00-ICT-TYP-SD-93 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1175 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 94 | 1300403-ATS-00-00-00-ICT-TYP-SD-94 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1176 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 95 | 1300403-ATS-00-00-00-ICT-TYP-SD-95 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1177 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 96 | 1300403-ATS-00-00-00-ICT-TYP-SD-96 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1178 | ICT | TYPICAL DRAWINGS | 1300403 | ATS | 00 | 00 | 0 | ICT | TYP | SD | 97 | 1300403-ATS-00-00-00-ICT-TYP-SD-97 | Typical Drawings | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1179 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | SCH | SD | 0 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-00 | Antenna Schedule For Gsm System Sheet-01 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1180 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | SCH | SD | 2 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-02 | Antenna Schedule For Gsm System Sheet-02 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1181 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | SCH | SD | 3 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-03 | Gsm Remote Units, Hubs And Poi'S Sheet-01 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1182 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | SCH | SD | 4 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-04 | Gsm Remote Units, Hubs And Poi'S Sheet-02 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1183 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX |  | ICT | SCH | SD | 5 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-05 | Antenna Schedule For Tetra System Sheet-01 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1184 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX |  | ICT | SCH | SD | 6 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-06 | Antenna Schedule For Tetra System Sheet-02 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1185 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX |  | ICT | SCH | SD | 7 | 1300403-ATS-BXX-XX-XX-ICT-SCH-SD-07 | Tetra Remote Units And Hubs Sheet-01 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1186 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | BF | 0 | ICT | GSM | SD | 1 | 1300403-ATS-B01-BF-00-ICT-GSM-SD-01 | B0001- Terminal Basement Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1187 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | GF | 0 | ICT | GSM | SD | 2 | 1300403-ATS-B01-GF-00-ICT-GSM-SD-02 | B0001 -Terminal Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1188 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | MZ | 0 | ICT | GSM | SD | 3 | 1300403-ATS-B01-MZ-00-ICT-GSM-SD-03 | B0001 -Terminal Mezzanine Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1189 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | FF | 0 | ICT | GSM | SD | 4 | 1300403-ATS-B01-FF-00-ICT-GSM-SD-04 | B0001- Terminal First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1190 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 0 | ICT | GSM | SD | 5 | 1300403-ATS-B02-GF-00-ICT-GSM-SD-05 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1191 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 1 | ICT | GSM | SD | 0 | 1300403-ATS-B02-GF-01-ICT-GSM-SD-00 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1192 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 2 | ICT | GSM | SD | 7 | 1300403-ATS-B02-GF-02-ICT-GSM-SD-07 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1193 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 3 | ICT | GSM | SD | 8 | 1300403-ATS-B02-GF-03-ICT-GSM-SD-08 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1194 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 0 | ICT | GSM | SD | 9 | 1300403-ATS-B02-FF-00-ICT-GSM-SD-09 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1195 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 1 | ICT | GSM | SD | 10 | 1300403-ATS-B02-FF-01-ICT-GSM-SD-10 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1196 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 2 | ICT | GSM | SD | 11 | 1300403-ATS-B02-FF-02-ICT-GSM-SD-11 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1197 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 3 | ICT | GSM | SD | 12 | 1300403-ATS-B02-FF-03-ICT-GSM-SD-12 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1198 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | BF | 0 | ICT | GSM | SD | 13 | 1300403-ATS-B03-BF-00-ICT-GSM-SD-13 | B0003- Mosque Basement Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1199 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 0 | ICT | GSM | SD | 14 | 1300403-ATS-B03-GF-00-ICT-GSM-SD-14 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1200 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 1 | ICT | GSM | SD | 15 | 1300403-ATS-B03-GF-01-ICT-GSM-SD-15 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1201 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 2 | ICT | GSM | SD | 16 | 1300403-ATS-B03-GF-02-ICT-GSM-SD-16 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1202 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 0 | ICT | GSM | SD | 17 | 1300403-ATS-B03-FF-00-ICT-GSM-SD-17 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1203 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 1 | ICT | GSM | SD | 18 | 1300403-ATS-B03-FF-01-ICT-GSM-SD-18 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1204 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 2 | ICT | GSM | SD | 19 | 1300403-ATS-B03-FF-02-ICT-GSM-SD-19 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1205 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 0 | ICT | GSM | SD | 20 | 1300403-ATS-B04-BF-00-ICT-GSM-SD-20 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1206 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 1 | ICT | GSM | SD | 21 | 1300403-ATS-B04-BF-01-ICT-GSM-SD-21 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1207 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 2 | ICT | GSM | SD | 22 | 1300403-ATS-B04-BF-02-ICT-GSM-SD-22 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1208 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 3 | ICT | GSM | SD | 23 | 1300403-ATS-B04-BF-03-ICT-GSM-SD-23 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1209 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 4 | ICT | GSM | SD | 24 | 1300403-ATS-B04-BF-04-ICT-GSM-SD-24 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1210 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 0 | ICT | GSM | SD | 25 | 1300403-ATS-B04-GF-00-ICT-GSM-SD-25 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1211 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 1 | ICT | GSM | SD | 26 | 1300403-ATS-B04-GF-01-ICT-GSM-SD-26 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1212 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 2 | ICT | GSM | SD | 27 | 1300403-ATS-B04-GF-02-ICT-GSM-SD-27 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1213 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 3 | ICT | GSM | SD | 28 | 1300403-ATS-B04-GF-03-ICT-GSM-SD-28 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1214 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 4 | ICT | GSM | SD | 29 | 1300403-ATS-B04-GF-04-ICT-GSM-SD-29 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1215 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 0 | ICT | GSM | SD | 30 | 1300403-ATS-B05-BF-00-ICT-GSM-SD-30 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1216 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 1 | ICT | GSM | SD | 31 | 1300403-ATS-B05-BF-01-ICT-GSM-SD-31 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1217 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 2 | ICT | GSM | SD | 32 | 1300403-ATS-B05-BF-02-ICT-GSM-SD-32 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1218 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 3 | ICT | GSM | SD | 33 | 1300403-ATS-B05-BF-03-ICT-GSM-SD-33 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1219 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 4 | ICT | GSM | SD | 34 | 1300403-ATS-B05-BF-04-ICT-GSM-SD-34 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 900 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1220 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B06 | GF | 0 | ICT | GSM | SD | 35 | 1300403-ATS-B06-GF-00-ICT-GSM-SD-35 | B0006 - Baggage Handling Area Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1221 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B07 | GF | 0 | ICT | GSM | SD | 36 | 1300403-ATS-B07-GF-00-ICT-GSM-SD-36 | B0007 - Hajj Building Ground Floor Gsm Das Prediction Heatmap At Frequency 900 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1222 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | BF | 0 | ICT | GSM | SD | 37 | 1300403-ATS-B01-BF-00-ICT-GSM-SD-37 | B0001- Terminal Basement Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1223 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | GF | 0 | ICT | GSM | SD | 38 | 1300403-ATS-B01-GF-00-ICT-GSM-SD-38 | B0001 -Terminal Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1224 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | MZ | 0 | ICT | GSM | SD | 39 | 1300403-ATS-B01-MZ-00-ICT-GSM-SD-39 | B0001 -Terminal Mezzanine Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1225 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | FF | 0 | ICT | GSM | SD | 40 | 1300403-ATS-B01-FF-00-ICT-GSM-SD-40 | B0001- Terminal First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1226 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 0 | ICT | GSM | SD | 41 | 1300403-ATS-B02-GF-00-ICT-GSM-SD-41 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1227 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 1 | ICT | GSM | SD | 42 | 1300403-ATS-B02-GF-01-ICT-GSM-SD-42 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1228 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 2 | ICT | GSM | SD | 43 | 1300403-ATS-B02-GF-02-ICT-GSM-SD-43 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1229 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 3 | ICT | GSM | SD | 44 | 1300403-ATS-B02-GF-03-ICT-GSM-SD-44 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1230 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 0 | ICT | GSM | SD | 45 | 1300403-ATS-B02-FF-00-ICT-GSM-SD-45 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1231 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 1 | ICT | GSM | SD | 46 | 1300403-ATS-B02-FF-01-ICT-GSM-SD-46 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1232 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 2 | ICT | GSM | SD | 47 | 1300403-ATS-B02-FF-02-ICT-GSM-SD-47 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1233 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 3 | ICT | GSM | SD | 48 | 1300403-ATS-B02-FF-03-ICT-GSM-SD-48 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1234 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | BF | 0 | ICT | GSM | SD | 49 | 1300403-ATS-B03-BF-00-ICT-GSM-SD-49 | B0003 -Mosque Basement Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1235 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 0 | ICT | GSM | SD | 50 | 1300403-ATS-B03-GF-00-ICT-GSM-SD-50 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1236 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 1 | ICT | GSM | SD | 51 | 1300403-ATS-B03-GF-01-ICT-GSM-SD-51 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1237 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 2 | ICT | GSM | SD | 52 | 1300403-ATS-B03-GF-02-ICT-GSM-SD-52 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1238 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 0 | ICT | GSM | SD | 53 | 1300403-ATS-B03-FF-00-ICT-GSM-SD-53 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1239 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 1 | ICT | GSM | SD | 54 | 1300403-ATS-B03-FF-01-ICT-GSM-SD-54 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1240 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 2 | ICT | GSM | SD | 55 | 1300403-ATS-B03-FF-02-ICT-GSM-SD-55 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1241 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 0 | ICT | GSM | SD | 56 | 1300403-ATS-B04-BF-00-ICT-GSM-SD-56 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1242 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 1 | ICT | GSM | SD | 57 | 1300403-ATS-B04-BF-01-ICT-GSM-SD-57 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1243 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 2 | ICT | GSM | SD | 58 | 1300403-ATS-B04-BF-02-ICT-GSM-SD-58 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1244 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 3 | ICT | GSM | SD | 59 | 1300403-ATS-B04-BF-03-ICT-GSM-SD-59 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1245 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 4 | ICT | GSM | SD | 60 | 1300403-ATS-B04-BF-04-ICT-GSM-SD-60 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1246 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 0 | ICT | GSM | SD | 61 | 1300403-ATS-B04-GF-00-ICT-GSM-SD-61 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1247 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 1 | ICT | GSM | SD | 62 | 1300403-ATS-B04-GF-01-ICT-GSM-SD-62 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1248 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 2 | ICT | GSM | SD | 63 | 1300403-ATS-B04-GF-02-ICT-GSM-SD-63 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1249 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 3 | ICT | GSM | SD | 64 | 1300403-ATS-B04-GF-03-ICT-GSM-SD-64 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1250 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 4 | ICT | GSM | SD | 65 | 1300403-ATS-B04-GF-04-ICT-GSM-SD-65 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1251 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 0 | ICT | GSM | SD | 66 | 1300403-ATS-B05-BF-00-ICT-GSM-SD-66 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1252 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 1 | ICT | GSM | SD | 67 | 1300403-ATS-B05-BF-01-ICT-GSM-SD-67 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1253 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 2 | ICT | GSM | SD | 68 | 1300403-ATS-B05-BF-02-ICT-GSM-SD-68 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1254 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 3 | ICT | GSM | SD | 69 | 1300403-ATS-B05-BF-03-ICT-GSM-SD-69 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1255 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 4 | ICT | GSM | SD | 70 | 1300403-ATS-B05-BF-04-ICT-GSM-SD-70 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 1800 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1256 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B06 | GF | 0 | ICT | GSM | SD | 71 | 1300403-ATS-B06-GF-00-ICT-GSM-SD-71 | B0006 - Baggage Handling Area Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1257 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B07 | GF | 0 | ICT | GSM | SD | 72 | 1300403-ATS-B07-GF-00-ICT-GSM-SD-72 | B0007 - Hajj Building Ground Floor Gsm Das Prediction Heatmap At Frequency 1800 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1258 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | BF | 0 | ICT | GSM | SD | 73 | 1300403-ATS-B01-BF-00-ICT-GSM-SD-73 | B0001- Terminal Basement Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1259 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | GF | 0 | ICT | GSM | SD | 74 | 1300403-ATS-B01-GF-00-ICT-GSM-SD-74 | B0001 -Terminal Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1260 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | MZ | 0 | ICT | GSM | SD | 75 | 1300403-ATS-B01-MZ-00-ICT-GSM-SD-75 | B0001 -Terminal Mezzanine Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1261 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | FF | 0 | ICT | GSM | SD | 76 | 1300403-ATS-B01-FF-00-ICT-GSM-SD-76 | B0001- Terminal First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1262 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 0 | ICT | GSM | SD | 77 | 1300403-ATS-B02-GF-00-ICT-GSM-SD-77 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1263 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 1 | ICT | GSM | SD | 78 | 1300403-ATS-B02-GF-01-ICT-GSM-SD-78 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1264 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 2 | ICT | GSM | SD | 79 | 1300403-ATS-B02-GF-02-ICT-GSM-SD-79 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1265 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 3 | ICT | GSM | SD | 80 | 1300403-ATS-B02-GF-03-ICT-GSM-SD-80 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1266 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 0 | ICT | GSM | SD | 81 | 1300403-ATS-B02-FF-00-ICT-GSM-SD-81 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1267 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 1 | ICT | GSM | SD | 82 | 1300403-ATS-B02-FF-01-ICT-GSM-SD-82 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1268 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 2 | ICT | GSM | SD | 83 | 1300403-ATS-B02-FF-02-ICT-GSM-SD-83 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1269 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 3 | ICT | GSM | SD | 84 | 1300403-ATS-B02-FF-03-ICT-GSM-SD-84 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1270 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | BF | 0 | ICT | GSM | SD | 85 | 1300403-ATS-B03-BF-00-ICT-GSM-SD-85 | B0003 -Mosque Basement Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1271 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 0 | ICT | GSM | SD | 86 | 1300403-ATS-B03-GF-00-ICT-GSM-SD-86 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Overall Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1272 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 1 | ICT | GSM | SD | 87 | 1300403-ATS-B03-GF-01-ICT-GSM-SD-87 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1273 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 2 | ICT | GSM | SD | 88 | 1300403-ATS-B03-GF-02-ICT-GSM-SD-88 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1274 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 0 | ICT | GSM | SD | 89 | 1300403-ATS-B03-FF-00-ICT-GSM-SD-89 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1275 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 1 | ICT | GSM | SD | 90 | 1300403-ATS-B03-FF-01-ICT-GSM-SD-90 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1276 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 2 | ICT | GSM | SD | 91 | 1300403-ATS-B03-FF-02-ICT-GSM-SD-91 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1277 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 0 | ICT | GSM | SD | 92 | 1300403-ATS-B04-BF-00-ICT-GSM-SD-92 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1278 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 1 | ICT | GSM | SD | 93 | 1300403-ATS-B04-BF-01-ICT-GSM-SD-93 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1279 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 2 | ICT | GSM | SD | 94 | 1300403-ATS-B04-BF-02-ICT-GSM-SD-94 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1280 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 3 | ICT | GSM | SD | 95 | 1300403-ATS-B04-BF-03-ICT-GSM-SD-95 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1281 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 4 | ICT | GSM | SD | 96 | 1300403-ATS-B04-BF-04-ICT-GSM-SD-96 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1282 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 0 | ICT | GSM | SD | 97 | 1300403-ATS-B04-GF-00-ICT-GSM-SD-97 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1283 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 1 | ICT | GSM | SD | 98 | 1300403-ATS-B04-GF-01-ICT-GSM-SD-98 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1284 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 2 | ICT | GSM | SD | 99 | 1300403-ATS-B04-GF-02-ICT-GSM-SD-99 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1285 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 3 | ICT | GSM | SD | 100 | 1300403-ATS-B04-GF-03-ICT-GSM-SD-100 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1286 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 4 | ICT | GSM | SD | 101 | 1300403-ATS-B04-GF-04-ICT-GSM-SD-101 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1287 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 0 | ICT | GSM | SD | 102 | 1300403-ATS-B05-BF-00-ICT-GSM-SD-102 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1288 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 1 | ICT | GSM | SD | 103 | 1300403-ATS-B05-BF-01-ICT-GSM-SD-103 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1289 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 2 | ICT | GSM | SD | 104 | 1300403-ATS-B05-BF-02-ICT-GSM-SD-104 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1290 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 3 | ICT | GSM | SD | 105 | 1300403-ATS-B05-BF-03-ICT-GSM-SD-105 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1291 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 4 | ICT | GSM | SD | 106 | 1300403-ATS-B05-BF-04-ICT-GSM-SD-106 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2100 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1292 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B06 | GF | 0 | ICT | GSM | SD | 107 | 1300403-ATS-B06-GF-00-ICT-GSM-SD-107 | B0006 - Baggage Handling Area Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1293 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B07 | GF | 0 | ICT | GSM | SD | 108 | 1300403-ATS-B07-GF-00-ICT-GSM-SD-108 | B0007 - Hajj Building Ground Floor Gsm Das Prediction Heatmap At Frequency 2100 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1294 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | BF | 0 | ICT | GSM | SD | 109 | 1300403-ATS-B01-BF-00-ICT-GSM-SD-109 | B0001- Terminal Basement Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1295 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | GF | 0 | ICT | GSM | SD | 110 | 1300403-ATS-B01-GF-00-ICT-GSM-SD-110 | B0001 -Terminal Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1296 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | MZ | 0 | ICT | GSM | SD | 111 | 1300403-ATS-B01-MZ-00-ICT-GSM-SD-111 | B0001 -Terminal Mezzanine Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1297 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | FF | 0 | ICT | GSM | SD | 112 | 1300403-ATS-B01-FF-00-ICT-GSM-SD-112 | B0001- Terminal First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1298 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 0 | ICT | GSM | SD | 113 | 1300403-ATS-B02-GF-00-ICT-GSM-SD-113 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1299 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 1 | ICT | GSM | SD | 114 | 1300403-ATS-B02-GF-01-ICT-GSM-SD-114 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1300 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 2 | ICT | GSM | SD | 115 | 1300403-ATS-B02-GF-02-ICT-GSM-SD-115 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1301 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 3 | ICT | GSM | SD | 116 | 1300403-ATS-B02-GF-03-ICT-GSM-SD-116 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1302 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 0 | ICT | GSM | SD | 117 | 1300403-ATS-B02-FF-00-ICT-GSM-SD-117 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1303 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 1 | ICT | GSM | SD | 118 | 1300403-ATS-B02-FF-01-ICT-GSM-SD-118 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1304 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 2 | ICT | GSM | SD | 119 | 1300403-ATS-B02-FF-02-ICT-GSM-SD-119 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1305 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 3 | ICT | GSM | SD | 120 | 1300403-ATS-B02-FF-03-ICT-GSM-SD-120 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1306 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | BF | 0 | ICT | GSM | SD | 121 | 1300403-ATS-B03-BF-00-ICT-GSM-SD-121 | B0003 -Mosque Basement Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1307 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 0 | ICT | GSM | SD | 122 | 1300403-ATS-B03-GF-00-ICT-GSM-SD-122 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1308 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 1 | ICT | GSM | SD | 123 | 1300403-ATS-B03-GF-01-ICT-GSM-SD-123 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1309 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 2 | ICT | GSM | SD | 124 | 1300403-ATS-B03-GF-02-ICT-GSM-SD-124 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1310 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 0 | ICT | GSM | SD | 125 | 1300403-ATS-B03-FF-00-ICT-GSM-SD-125 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1311 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 1 | ICT | GSM | SD | 126 | 1300403-ATS-B03-FF-01-ICT-GSM-SD-126 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1312 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 2 | ICT | GSM | SD | 127 | 1300403-ATS-B03-FF-02-ICT-GSM-SD-127 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1313 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 0 | ICT | GSM | SD | 128 | 1300403-ATS-B04-BF-00-ICT-GSM-SD-128 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1314 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 1 | ICT | GSM | SD | 129 | 1300403-ATS-B04-BF-01-ICT-GSM-SD-129 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1315 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 2 | ICT | GSM | SD | 130 | 1300403-ATS-B04-BF-02-ICT-GSM-SD-130 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1316 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 3 | ICT | GSM | SD | 131 | 1300403-ATS-B04-BF-03-ICT-GSM-SD-131 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1317 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 4 | ICT | GSM | SD | 132 | 1300403-ATS-B04-BF-04-ICT-GSM-SD-132 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1318 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 0 | ICT | GSM | SD | 133 | 1300403-ATS-B04-GF-00-ICT-GSM-SD-133 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1319 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 1 | ICT | GSM | SD | 134 | 1300403-ATS-B04-GF-01-ICT-GSM-SD-134 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1320 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 2 | ICT | GSM | SD | 135 | 1300403-ATS-B04-GF-02-ICT-GSM-SD-135 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1321 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 3 | ICT | GSM | SD | 136 | 1300403-ATS-B04-GF-03-ICT-GSM-SD-136 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1322 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 4 | ICT | GSM | SD | 137 | 1300403-ATS-B04-GF-04-ICT-GSM-SD-137 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1323 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 0 | ICT | GSM | SD | 138 | 1300403-ATS-B05-BF-00-ICT-GSM-SD-138 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1324 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 1 | ICT | GSM | SD | 139 | 1300403-ATS-B05-BF-01-ICT-GSM-SD-139 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1325 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 2 | ICT | GSM | SD | 140 | 1300403-ATS-B05-BF-02-ICT-GSM-SD-140 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1326 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 3 | ICT | GSM | SD | 141 | 1300403-ATS-B05-BF-03-ICT-GSM-SD-141 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1327 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 4 | ICT | GSM | SD | 142 | 1300403-ATS-B05-BF-04-ICT-GSM-SD-142 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2300 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1328 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B06 | GF | 0 | ICT | GSM | SD | 143 | 1300403-ATS-B06-GF-00-ICT-GSM-SD-143 | B0006 - Baggage Handling Area Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1329 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B07 | GF | 0 | ICT | GSM | SD | 144 | 1300403-ATS-B07-GF-00-ICT-GSM-SD-144 | B0007 - Hajj Building Ground Floor Gsm Das Prediction Heatmap At Frequency 2300 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1330 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | BF | 0 | ICT | GSM | SD | 145 | 1300403-ATS-B01-BF-00-ICT-GSM-SD-145 | B0001- Terminal Basement Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1331 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | GF | 0 | ICT | GSM | SD | 146 | 1300403-ATS-B01-GF-00-ICT-GSM-SD-146 | B0001 -Terminal Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1332 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | MZ | 0 | ICT | GSM | SD | 147 | 1300403-ATS-B01-MZ-00-ICT-GSM-SD-147 | B0001 -Terminal Mezzanine Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1333 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | FF | 0 | ICT | GSM | SD | 148 | 1300403-ATS-B01-FF-00-ICT-GSM-SD-148 | B0001- Terminal First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1334 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 0 | ICT | GSM | SD | 149 | 1300403-ATS-B02-GF-00-ICT-GSM-SD-149 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1335 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 1 | ICT | GSM | SD | 150 | 1300403-ATS-B02-GF-01-ICT-GSM-SD-150 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1336 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 2 | ICT | GSM | SD | 151 | 1300403-ATS-B02-GF-02-ICT-GSM-SD-151 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1337 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 3 | ICT | GSM | SD | 152 | 1300403-ATS-B02-GF-03-ICT-GSM-SD-152 | B0002- Group Check In Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1338 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 0 | ICT | GSM | SD | 153 | 1300403-ATS-B02-FF-00-ICT-GSM-SD-153 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1339 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 1 | ICT | GSM | SD | 154 | 1300403-ATS-B02-FF-01-ICT-GSM-SD-154 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1340 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 2 | ICT | GSM | SD | 155 | 1300403-ATS-B02-FF-02-ICT-GSM-SD-155 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1341 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 3 | ICT | GSM | SD | 156 | 1300403-ATS-B02-FF-03-ICT-GSM-SD-156 | B0002- Group Check In First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1342 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | BF | 0 | ICT | GSM | SD | 157 | 1300403-ATS-B03-BF-00-ICT-GSM-SD-157 | B0003 -Mosque Basement Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1343 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 0 | ICT | GSM | SD | 158 | 1300403-ATS-B03-GF-00-ICT-GSM-SD-158 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1344 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 1 | ICT | GSM | SD | 159 | 1300403-ATS-B03-GF-01-ICT-GSM-SD-159 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz -Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1345 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 2 | ICT | GSM | SD | 160 | 1300403-ATS-B03-GF-02-ICT-GSM-SD-160 | B0003 -Mosque Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz -Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1346 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 0 | ICT | GSM | SD | 161 | 1300403-ATS-B03-FF-00-ICT-GSM-SD-161 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1347 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 1 | ICT | GSM | SD | 162 | 1300403-ATS-B03-FF-01-ICT-GSM-SD-162 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1348 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 2 | ICT | GSM | SD | 163 | 1300403-ATS-B03-FF-02-ICT-GSM-SD-163 | B0003 -Mosque First Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1349 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 0 | ICT | GSM | SD | 164 | 1300403-ATS-B04-BF-00-ICT-GSM-SD-164 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Over All Layout | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1350 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 1 | ICT | GSM | SD | 165 | 1300403-ATS-B04-BF-01-ICT-GSM-SD-165 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 1 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1351 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 2 | ICT | GSM | SD | 166 | 1300403-ATS-B04-BF-02-ICT-GSM-SD-166 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 2 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1352 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 3 | ICT | GSM | SD | 167 | 1300403-ATS-B04-BF-03-ICT-GSM-SD-167 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 3 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1353 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 4 | ICT | GSM | SD | 168 | 1300403-ATS-B04-BF-04-ICT-GSM-SD-168 | B0004 -West Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 4 | 2025-06-30 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1354 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 0 | ICT | GSM | SD | 169 | 1300403-ATS-B04-GF-00-ICT-GSM-SD-169 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Over All Layout | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1355 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 1 | ICT | GSM | SD | 170 | 1300403-ATS-B04-GF-01-ICT-GSM-SD-170 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 1 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1356 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 2 | ICT | GSM | SD | 171 | 1300403-ATS-B04-GF-02-ICT-GSM-SD-171 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 2 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1357 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 3 | ICT | GSM | SD | 172 | 1300403-ATS-B04-GF-03-ICT-GSM-SD-172 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 3 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1358 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 4 | ICT | GSM | SD | 173 | 1300403-ATS-B04-GF-04-ICT-GSM-SD-173 | B0004 -West Parking Upper Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 4 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1359 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 0 | ICT | GSM | SD | 174 | 1300403-ATS-B05-BF-00-ICT-GSM-SD-174 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Over All Layout | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1360 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 1 | ICT | GSM | SD | 175 | 1300403-ATS-B05-BF-01-ICT-GSM-SD-175 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 1 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1361 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 2 | ICT | GSM | SD | 176 | 1300403-ATS-B05-BF-02-ICT-GSM-SD-176 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 2 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1362 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 3 | ICT | GSM | SD | 177 | 1300403-ATS-B05-BF-03-ICT-GSM-SD-177 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 3 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1363 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 4 | ICT | GSM | SD | 178 | 1300403-ATS-B05-BF-04-ICT-GSM-SD-178 | B0005 -East Parking Lower Level Gsm Das Prediction Heatmap At Frequency 2600 Mhz - Part 4 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1364 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B06 | GF | 0 | ICT | GSM | SD | 179 | 1300403-ATS-B06-GF-00-ICT-GSM-SD-179 | B0006 - Baggage Handling Area Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1365 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B07 | GF | 0 | ICT | GSM | SD | 180 | 1300403-ATS-B07-GF-00-ICT-GSM-SD-180 | B0007 - Hajj Building Ground Floor Gsm Das Prediction Heatmap At Frequency 2600 Mhz | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1366 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | BF | 0 | ICT | GSM | SD | 181 | 1300403-ATS-B01-BF-00-ICT-GSM-SD-181 | B0001 - Terminal Basement Floor Gsm Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1367 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | GF | 0 | ICT | GSM | SD | 182 | 1300403-ATS-B01-GF-00-ICT-GSM-SD-182 | B0001 - Terminal Ground Floor Gsm Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1368 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | MZ | 0 | ICT | GSM | SD | 183 | 1300403-ATS-B01-MZ-00-ICT-GSM-SD-183 | B0001 - Terminal Mezzanine Floor Gsm Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1369 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B01 | FF | 0 | ICT | GSM | SD | 184 | 1300403-ATS-B01-FF-00-ICT-GSM-SD-184 | B0001 - Terminal First Floor Gsm Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1370 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 0 | ICT | GSM | SD | 186 | 1300403-ATS-B02-GF-00-ICT-GSM-SD-186 | B0002- Group Check In Ground Floor Gsm Das Plan Over All Layout | 2025-07-02 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1371 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 1 | ICT | GSM | SD | 187 | 1300403-ATS-B02-GF-01-ICT-GSM-SD-187 | B0002- Group Check In Ground Floor Gsm Das Plan Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1372 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 2 | ICT | GSM | SD | 188 | 1300403-ATS-B02-GF-02-ICT-GSM-SD-188 | B0002- Group Check In Ground Floor Gsm Das Plan Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1373 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | GF | 3 | ICT | GSM | SD | 189 | 1300403-ATS-B02-GF-03-ICT-GSM-SD-189 | B0002- Group Check In Ground Floor Gsm Das Plan Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1374 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 0 | ICT | GSM | SD | 190 | 1300403-ATS-B02-FF-00-ICT-GSM-SD-190 | B0002- Group Check In First Floor Gsm Das Plan Over All Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1375 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 1 | ICT | GSM | SD | 191 | 1300403-ATS-B02-FF-01-ICT-GSM-SD-191 | B0002- Group Check In First Floor Gsm Das Plan Part 1 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1376 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 2 | ICT | GSM | SD | 192 | 1300403-ATS-B02-FF-02-ICT-GSM-SD-192 | B0002- Group Check In First Floor Gsm Das Plan Part 2 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1377 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B02 | FF | 3 | ICT | GSM | SD | 193 | 1300403-ATS-B02-FF-03-ICT-GSM-SD-193 | B0002- Group Check In First Floor Gsm Das Plan Part 3 | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1378 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | BF | 0 | ICT | GSM | SD | 194 | 1300403-ATS-B03-BF-00-ICT-GSM-SD-194 | B0003 - Mosque Basement Floor Gsm Das Plan Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1379 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 0 | ICT | GSM | SD | 195 | 1300403-ATS-B03-GF-00-ICT-GSM-SD-195 | B0003 - Mosque Ground Floor Gsm Das Plan Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1380 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 1 | ICT | GSM | SD | 196 | 1300403-ATS-B03-GF-01-ICT-GSM-SD-196 | B0003 - Mosque Ground Floor Gsm Das Plan Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1381 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | GF | 2 | ICT | GSM | SD | 197 | 1300403-ATS-B03-GF-02-ICT-GSM-SD-197 | B0003 - Mosque Ground Floor Gsm Das Plan Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1382 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 0 | ICT | GSM | SD | 198 | 1300403-ATS-B03-FF-00-ICT-GSM-SD-198 | B0003 - Mosque First Floor Gsm Das Plan Over All Layout | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1383 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 1 | ICT | GSM | SD | 199 | 1300403-ATS-B03-FF-01-ICT-GSM-SD-199 | B0003 - Mosque First Floor Gsm Das Plan Part 1 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1384 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B03 | FF | 2 | ICT | GSM | SD | 200 | 1300403-ATS-B03-FF-02-ICT-GSM-SD-200 | B0003 - Mosque First Floor Gsm Das Plan Part 2 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1385 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 0 | ICT | GSM | SD | 201 | 1300403-ATS-B04-BF-00-ICT-GSM-SD-201 | B0004 - West Parking Lower Level Gsm Das Plan Over Layout | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1386 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 1 | ICT | GSM | SD | 202 | 1300403-ATS-B04-BF-01-ICT-GSM-SD-202 | B0004 - West Parking Lower Level Gsm Das Plan Part 1 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1387 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 2 | ICT | GSM | SD | 203 | 1300403-ATS-B04-BF-02-ICT-GSM-SD-203 | B0004 - West Parking Lower Level Gsm Das Plan Part 2 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1388 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 3 | ICT | GSM | SD | 204 | 1300403-ATS-B04-BF-03-ICT-GSM-SD-204 | B0004 - West Parking Lower Level Gsm Das Plan Part 3 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1389 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | BF | 4 | ICT | GSM | SD | 205 | 1300403-ATS-B04-BF-04-ICT-GSM-SD-205 | B0004 - West Parking Lower Level Gsm Das Plan Part 4 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1390 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 0 | ICT | GSM | SD | 206 | 1300403-ATS-B04-GF-00-ICT-GSM-SD-206 | B0004 - West Parking Upper Level Gsm Das Plan Over All Layout | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1391 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 1 | ICT | GSM | SD | 207 | 1300403-ATS-B04-GF-01-ICT-GSM-SD-207 | B0004 - West Parking Upper Level Gsm Das Plan Part 1 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1392 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 2 | ICT | GSM | SD | 208 | 1300403-ATS-B04-GF-02-ICT-GSM-SD-208 | B0004 - West Parking Upper Level Gsm Das Plan Part 2 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1393 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 3 | ICT | GSM | SD | 209 | 1300403-ATS-B04-GF-03-ICT-GSM-SD-209 | B0004 - West Parking Upper Level Gsm Das Plan Part 3 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1394 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B04 | GF | 4 | ICT | GSM | SD | 210 | 1300403-ATS-B04-GF-04-ICT-GSM-SD-210 | B0004 - West Parking Upper Level Gsm Das Plan Part 4 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1395 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 0 | ICT | GSM | SD | 211 | 1300403-ATS-B05-BF-00-ICT-GSM-SD-211 | B0005 - East Parking Lower Level Gsm Das Plan Over All Layout | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1396 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 1 | ICT | GSM | SD | 212 | 1300403-ATS-B05-BF-01-ICT-GSM-SD-212 | B0005 - East Parking Lower Level Gsm Das Plan Part 1 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1397 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 2 | ICT | GSM | SD | 213 | 1300403-ATS-B05-BF-02-ICT-GSM-SD-213 | B0005 - East Parking Lower Level Gsm Das Plan Part 2 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1398 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 3 | ICT | GSM | SD | 214 | 1300403-ATS-B05-BF-03-ICT-GSM-SD-214 | B0005 - East Parking Lower Level Gsm Das Plan Part 3 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1399 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B05 | BF | 4 | ICT | GSM | SD | 215 | 1300403-ATS-B05-BF-04-ICT-GSM-SD-215 | B0005 - East Parking Lower Level Gsm Das Plan Part 4 | 2025-07-14 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1400 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B06 | GF | 0 | ICT | GSM | SD | 216 | 1300403-ATS-B06-GF-00-ICT-GSM-SD-216 | B0006 - Baggage Handling Area Gsm Das Plan Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1401 | GSM-DAS & TETRA | GSM | 1300403 | ATS | B07 | GF | 0 | ICT | GSM | SD | 217 | 1300403-ATS-B07-GF-00-ICT-GSM-SD-217 | B0007 - Hajj Building Gsm Das Plan Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1402 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | SLD | SD | 1 | 1300403-ATS-BXX-XX-XX-ICT-SLD-SD-01 | Single Line Diagram For Gsm System | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1403 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | RCK | SD | 1 | 1300403-ATS-BXX-XX-XX-ICT-RCK-SD-01 | Rack Elevation For Gsm System Sheet - 01 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1404 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | RCK | SD | 2 | 1300403-ATS-BXX-XX-XX-ICT-RCK-SD-02 | Rack Elevation For Gsm System Sheet - 02 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1405 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | RCK | SD | 3 | 1300403-ATS-BXX-XX-XX-ICT-RCK-SD-03 | Rack Elevation For Gsm System Sheet - 03 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1406 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | RCK | SD | 4 | 1300403-ATS-BXX-XX-XX-ICT-RCK-SD-04 | Rack Elevation For Gsm System Sheet - 04 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1407 | GSM-DAS & TETRA | GSM | 1300403 | ATS | BXX | XX |  | ICT | RCK | SD | 5 | 1300403-ATS-BXX-XX-XX-ICT-RCK-SD-05 | Rack Elevation For Gsm System Sheet - 05 | 2025-06-25 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1408 | GSM-DAS & TETRA | ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 2 | ICT | DET | SD | 0 | 1300403-ATS-BXX-XX-02-ICT-DET-SD-00 | Installation And Mounting Details Sheet-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1409 | GSM-DAS & TETRA | ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 3 | ICT | DET | SD | 0 | 1300403-ATS-BXX-XX-03-ICT-DET-SD-00 | Installation And Mounting Details Sheet-02 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1410 | GSM-DAS & TETRA | ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 4 | ICT | DET | SD | 0 | 1300403-ATS-BXX-XX-04-ICT-DET-SD-00 | Installation And Mounting Details Sheet-03 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1411 | GSM-DAS & TETRA | ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 0 | ICT | DET | SD | 0 | 1300403-ATS-BXX-XX-00-ICT-DET-SD-00 | Installation And Mounting Details Sheet-04 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1412 | GSM-DAS & TETRA | ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 1 | ICT | DET | SD | 0 | 1300403-ATS-BXX-XX-01-ICT-DET-SD-00 | Installation And Mounting Details Sheet-01 | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1413 | GSM-DAS & TETRA | ICT TECHNICAL ROOMS | 1300403 | ATS | BXX | XX | 2 | ICT | DET | SD | 1 | 1300403-ATS-BXX-XX-02-ICT-DET-SD-01 | Gsm & Tetra System Room Layout(B001-Gr-450) | 2025-06-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1414 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 0 | ICT | TET | SD | 0 | 1300403-ATS-B01-BF-00-ICT-TET-SD-00 | B0001 - Terminal Basement Floor Tetra Das Prediction Heatmap | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1415 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 0 | ICT | TET | SD | 2 | 1300403-ATS-B01-GF-00-ICT-TET-SD-02 | B0001 - Terminal Ground Floor Tetra Das Prediction Heatmap | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1416 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 0 | ICT | TET | SD | 3 | 1300403-ATS-B01-MZ-00-ICT-TET-SD-03 | B0001 - Terminal Mezzanine Floor Tetra Das Prediction Heatmap | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1417 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 0 | ICT | TET | SD | 4 | 1300403-ATS-B01-FF-00-ICT-TET-SD-04 | B0001 - Terminal First Floor Tetra Das Prediction Heatmap | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1418 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 0 | ICT | TET | SD | 5 | 1300403-ATS-B02-GF-00-ICT-TET-SD-05 | B0002 - Group Check In Ground Floor Tetra Das Prediction Heatmap Over All Layout | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1419 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 1 | ICT | TET | SD | 6 | 1300403-ATS-B02-GF-01-ICT-TET-SD-06 | B0002 - Group Check In Ground Floor Tetra Das Prediction Heatmap Part 1 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1420 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 2 | ICT | TET | SD | 7 | 1300403-ATS-B02-GF-02-ICT-TET-SD-07 | B0002 - Group Check In Ground Floor Tetra Das Prediction Heatmap Part 2 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1421 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 3 | ICT | TET | SD | 8 | 1300403-ATS-B02-GF-03-ICT-TET-SD-08 | B0002 - Group Check In Ground Floor Tetra Das Prediction Heatmap Part 3 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1422 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 0 | ICT | TET | SD | 9 | 1300403-ATS-B02-FF-00-ICT-TET-SD-09 | B0002 - Group Check In First Floor Tetra Das Prediction Heatmap Over All Layout | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1423 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 1 | ICT | TET | SD | 10 | 1300403-ATS-B02-FF-01-ICT-TET-SD-10 | B0002 - Group Check In First Floor Tetra Das Prediction Heatmap Part 1 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1424 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 2 | ICT | TET | SD | 11 | 1300403-ATS-B02-FF-02-ICT-TET-SD-11 | B0002 - Group Check In First Floor Tetra Das Prediction Heatmap Part 2 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1425 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 3 | ICT | TET | SD | 12 | 1300403-ATS-B02-FF-03-ICT-TET-SD-12 | B0002 - Group Check In First Floor Tetra Das Prediction Heatmap Part 3 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1426 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | BF | 0 | ICT | TET | SD | 13 | 1300403-ATS-B03-BF-00-ICT-TET-SD-13 | B0003 - Mosque Basement Floor Tetra Das Prediction Heatmap | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1427 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 0 | ICT | TET | SD | 14 | 1300403-ATS-B03-GF-00-ICT-TET-SD-14 | B0003 - Mosque Ground Floor Tetra Das Prediction Heatmap Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1428 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 1 | ICT | TET | SD | 15 | 1300403-ATS-B03-GF-01-ICT-TET-SD-15 | B0003 - Mosque Ground Floor Tetra Das Prediction Heatmap Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1429 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 2 | ICT | TET | SD | 16 | 1300403-ATS-B03-GF-02-ICT-TET-SD-16 | B0003 - Mosque Ground Floor Tetra Das Prediction Heatmap Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1430 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 0 | ICT | TET | SD | 17 | 1300403-ATS-B03-FF-00-ICT-TET-SD-17 | B0003 - Mosque First Floor Tetra Das Prediction Heatmap Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1431 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 1 | ICT | TET | SD | 18 | 1300403-ATS-B03-FF-01-ICT-TET-SD-18 | B0003 - Mosque First Floor Tetra Das Prediction Heatmap Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1432 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 2 | ICT | TET | SD | 19 | 1300403-ATS-B03-FF-02-ICT-TET-SD-19 | B0003 - Mosque First Floor Tetra Das Prediction Heatmap Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1433 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 0 | ICT | TET | SD | 20 | 1300403-ATS-B04-BF-00-ICT-TET-SD-20 | B0004 - West Parking Lower Level Tetra Das Prediction Heatmap Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1434 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 1 | ICT | TET | SD | 21 | 1300403-ATS-B04-BF-01-ICT-TET-SD-21 | B0004 - West Parking Lower Level Tetra Das Prediction Heatmap Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1435 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 2 | ICT | TET | SD | 22 | 1300403-ATS-B04-BF-02-ICT-TET-SD-22 | B0004 - West Parking Lower Level Tetra Das Prediction Heatmap Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1436 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 3 | ICT | TET | SD | 23 | 1300403-ATS-B04-BF-03-ICT-TET-SD-23 | B0004 - West Parking Lower Level Tetra Das Prediction Heatmap Part 3 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1437 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 4 | ICT | TET | SD | 24 | 1300403-ATS-B04-BF-04-ICT-TET-SD-24 | B0004 - West Parking Lower Level Tetra Das Prediction Heatmap Part 4 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1438 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 0 | ICT | TET | SD | 25 | 1300403-ATS-B04-GF-00-ICT-TET-SD-25 | B0004 - West Parking Upper Level Tetra Das Prediction Heatmap Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1439 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 1 | ICT | TET | SD | 26 | 1300403-ATS-B04-GF-01-ICT-TET-SD-26 | B0004 - West Parking Upper Level Tetra Das Prediction Heatmap Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1440 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 2 | ICT | TET | SD | 27 | 1300403-ATS-B04-GF-02-ICT-TET-SD-27 | B0004 - West Parking Upper Level Tetra Das Prediction Heatmap Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1441 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 3 | ICT | TET | SD | 28 | 1300403-ATS-B04-GF-03-ICT-TET-SD-28 | B0004 - West Parking Upper Level Tetra Das Prediction Heatmap Part 3 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1442 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 4 | ICT | TET | SD | 29 | 1300403-ATS-B04-GF-04-ICT-TET-SD-29 | B0004 - West Parking Upper Level Tetra Das Prediction Heatmap Part 4 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1443 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 0 | ICT | TET | SD | 30 | 1300403-ATS-B05-BF-00-ICT-TET-SD-30 | B0005 - East Parking Lower Level Tetra Das Prediction Heatmap Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1444 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 1 | ICT | TET | SD | 31 | 1300403-ATS-B05-BF-01-ICT-TET-SD-31 | B0005 - East Parking Lower Level Tetra Das Prediction Heatmap Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1445 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 2 | ICT | TET | SD | 32 | 1300403-ATS-B05-BF-02-ICT-TET-SD-32 | B0005 - East Parking Lower Level Tetra Das Prediction Heatmap Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1446 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 3 | ICT | TET | SD | 33 | 1300403-ATS-B05-BF-03-ICT-TET-SD-33 | B0005 - East Parking Lower Level Tetra Das Prediction Heatmap Part 3 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1447 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 4 | ICT | TET | SD | 34 | 1300403-ATS-B05-BF-04-ICT-TET-SD-34 | B0005 - East Parking Lower Level Tetra Das Prediction Heatmap Part 4 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1448 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B06 | GF | 0 | ICT | TET | SD | 35 | 1300403-ATS-B06-GF-00-ICT-TET-SD-35 | B0006 - Baggage Handling Area Tetra Das Prediction Heatmap | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1449 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B07 | GF | 0 | ICT | TET | SD | 36 | 1300403-ATS-B07-GF-00-ICT-TET-SD-36 | B0007 - Hajj Building Tetra Das Prediction Heatmap | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1450 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | BF | 0 | ICT | TET | SD | 37 | 1300403-ATS-B01-BF-00-ICT-TET-SD-37 | B0001 - Terminal Basement Floor Tetra Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1451 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | GF | 0 | ICT | TET | SD | 38 | 1300403-ATS-B01-GF-00-ICT-TET-SD-38 | B0001 - Terminal Ground Floor Tetra Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1452 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | MZ | 0 | ICT | TET | SD | 39 | 1300403-ATS-B01-MZ-00-ICT-TET-SD-39 | B0001 - Terminal Mezzanine Floor Tetra Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1453 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B01 | FF | 0 | ICT | TET | SD | 40 | 1300403-ATS-B01-FF-00-ICT-TET-SD-40 | B0001 - Terminal First Floor Tetra Das Plan Layout | 2025-06-23 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1454 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 0 | ICT | TET | SD | 41 | 1300403-ATS-B02-GF-00-ICT-TET-SD-41 | B0002 - Group Check In Ground Floor Tetra Das Plan Over All Layout | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1455 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 1 | ICT | TET | SD | 42 | 1300403-ATS-B02-GF-01-ICT-TET-SD-42 | B0002 - Group Check In Ground Floor Tetra Das Plan Part 1 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1456 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 2 | ICT | TET | SD | 43 | 1300403-ATS-B02-GF-02-ICT-TET-SD-43 | B0002 - Group Check In Ground Floor Tetra Das Plan Part 2 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1457 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | GF | 3 | ICT | TET | SD | 44 | 1300403-ATS-B02-GF-03-ICT-TET-SD-44 | B0002 - Group Check In Ground Floor Tetra Das Plan Part 3 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1458 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 0 | ICT | TET | SD | 45 | 1300403-ATS-B02-FF-00-ICT-TET-SD-45 | B0002 - Group Check In First Floor Tetra Das Plan Over All Layout | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1459 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 1 | ICT | TET | SD | 46 | 1300403-ATS-B02-FF-01-ICT-TET-SD-46 | B0002 - Group Check In First Floor Tetra Das Plan Part 1 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1460 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 2 | ICT | TET | SD | 47 | 1300403-ATS-B02-FF-02-ICT-TET-SD-47 | B0002 - Group Check In First Floor Tetra Das Plan Part 2 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1461 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B02 | FF | 3 | ICT | TET | SD | 48 | 1300403-ATS-B02-FF-03-ICT-TET-SD-48 | B0002 - Group Check In First Floor Tetra Das Plan Part 3 | 2025-07-06 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1462 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | BF | 0 | ICT | TET | SD | 49 | 1300403-ATS-B03-BF-00-ICT-TET-SD-49 | B0003 - Mosque Basement Floor Tetra Das Plan Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1463 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 0 | ICT | TET | SD | 50 | 1300403-ATS-B03-GF-00-ICT-TET-SD-50 | B0003 - Mosque Ground Floor Tetra Das Plan Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1464 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 1 | ICT | TET | SD | 51 | 1300403-ATS-B03-GF-01-ICT-TET-SD-51 | B0003 - Mosque Ground Floor Tetra Das Plan Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1465 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | GF | 2 | ICT | TET | SD | 52 | 1300403-ATS-B03-GF-02-ICT-TET-SD-52 | B0003 - Mosque Ground Floor Tetra Das Plan Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1466 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 0 | ICT | TET | SD | 53 | 1300403-ATS-B03-FF-00-ICT-TET-SD-53 | B0003 - Mosque First Floor Tetra Das Plan Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1467 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 1 | ICT | TET | SD | 54 | 1300403-ATS-B03-FF-01-ICT-TET-SD-54 | B0003 - Mosque First Floor Tetra Das Plan Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1468 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B03 | FF | 2 | ICT | TET | SD | 55 | 1300403-ATS-B03-FF-02-ICT-TET-SD-55 | B0003 - Mosque First Floor Tetra Das Plan Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1469 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 0 | ICT | TET | SD | 56 | 1300403-ATS-B04-BF-00-ICT-TET-SD-56 | B0004 - West Parking Lower Level Tetra Das Plan Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1470 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 1 | ICT | TET | SD | 57 | 1300403-ATS-B04-BF-01-ICT-TET-SD-57 | B0004 - West Parking Lower Level Tetra Das Plan Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1471 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 2 | ICT | TET | SD | 58 | 1300403-ATS-B04-BF-02-ICT-TET-SD-58 | B0004 - West Parking Lower Level Tetra Das Plan Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1472 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 3 | ICT | TET | SD | 59 | 1300403-ATS-B04-BF-03-ICT-TET-SD-59 | B0004 - West Parking Lower Level Tetra Das Plan Part 3 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1473 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | BF | 4 | ICT | TET | SD | 60 | 1300403-ATS-B04-BF-04-ICT-TET-SD-60 | B0004 - West Parking Lower Level Tetra Das Plan Part 4 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1474 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 0 | ICT | TET | SD | 61 | 1300403-ATS-B04-GF-00-ICT-TET-SD-61 | B0004 - West Parking Upper Level Tetra Das Plan Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1475 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 1 | ICT | TET | SD | 62 | 1300403-ATS-B04-GF-01-ICT-TET-SD-62 | B0004 - West Parking Upper Level Tetra Das Plan Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1476 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 2 | ICT | TET | SD | 63 | 1300403-ATS-B04-GF-02-ICT-TET-SD-63 | B0004 - West Parking Upper Level Tetra Das Plan Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1477 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 3 | ICT | TET | SD | 64 | 1300403-ATS-B04-GF-03-ICT-TET-SD-64 | B0004 - West Parking Upper Level Tetra Das Plan Part 3 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1478 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B04 | GF | 4 | ICT | TET | SD | 65 | 1300403-ATS-B04-GF-04-ICT-TET-SD-65 | B0004 - West Parking Upper Level Tetra Das Plan Part 4 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1479 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 0 | ICT | TET | SD | 66 | 1300403-ATS-B05-BF-00-ICT-TET-SD-66 | B0005 - East Parking Lower Level Tetra Das Plan Over All Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1480 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 1 | ICT | TET | SD | 67 | 1300403-ATS-B05-BF-01-ICT-TET-SD-67 | B0005 - East Parking Lower Level Tetra Das Plan Part 1 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1481 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 2 | ICT | TET | SD | 68 | 1300403-ATS-B05-BF-02-ICT-TET-SD-68 | B0005 - East Parking Lower Level Tetra Das Plan Part 2 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1482 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 3 | ICT | TET | SD | 69 | 1300403-ATS-B05-BF-03-ICT-TET-SD-69 | B0005 - East Parking Lower Level Tetra Das Plan Part 3 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1483 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B05 | BF | 4 | ICT | TET | SD | 70 | 1300403-ATS-B05-BF-04-ICT-TET-SD-70 | B0005 - East Parking Lower Level Tetra Das Plan Part 4 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1484 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B06 | GF | 0 | ICT | TET | SD | 71 | 1300403-ATS-B06-GF-00-ICT-TET-SD-71 | B0006 - Baggage Handling Area Tetra Das Plan Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1485 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | B07 | GF | 0 | ICT | TET | SD | 72 | 1300403-ATS-B07-GF-00-ICT-TET-SD-72 | B0007 - Hajj Building Tetra Das Plan Layout | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1486 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 0 | ICT | SLD | SD | 2 | 1300403-ATS-BXX-XX-00-ICT-SLD-SD-02 | Single Line Diagram For Tetra System | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1487 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 0 | ICT | RCK | SD | 6 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-06 | Rack Elevation For Tetra System Sheet - 01 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1488 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 0 | ICT | RCK | SD | 7 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-07 | Rack Elevation For Tetra System Sheet - 02 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1489 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 0 | ICT | RCK | SD | 8 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-08 | Rack Elevation For Tetra System Sheet - 03 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1490 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 0 | ICT | RCK | SD | 9 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-09 | Rack Elevation For Tetra System Sheet - 04 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1491 | GSM-DAS & TETRA | TETRA | 1300403 | ATS | BXX | XX | 0 | ICT | RCK | SD | 10 | 1300403-ATS-BXX-XX-00-ICT-RCK-SD-10 | Rack Elevation For Tetra System Sheet - 05 | 2025-06-18 | --- | --- |  | --- |  | --- | --- |  | --- | [6 empty] | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1492 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 0 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-00-ICT-CNT-SD-00 | Terminal Basement Contaiment Overall Plan | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1493 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 1 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-01-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-01 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1494 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 2 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-02-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-02 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1495 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 3 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-03-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-03 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1496 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 4 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-04-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-04 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1497 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 5 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-05-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-05 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1498 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 6 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-06-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-06 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1499 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 7 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-07-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-07 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1500 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 8 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-08-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-08 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1501 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 9 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-09-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-09 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1502 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 10 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-10-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-10 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1503 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 11 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-11-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-11 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---
1504 | ICT | CONTAINMENT SYSTEM | 1300403 | ATS | B01 | BF | 12 | ICT | CNT | SD | 0 | 1300403-ATS-B01-BF-12-ICT-CNT-SD-00 | Terminal Basement Contaiment Plan Part-12 | 2025-05-16 | 3 | --- | 0 | 45794 | ATLS-004-SD-ICT-00002-R00 | Code 2 | 20 May 25 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 |  | ATLS-004-SD-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | 2025-05-17 | ATV-1300000403-SDS-ICT-00002-R00 | Code 2 | 2025-05-20 | Code 2 |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | --- |  |  |  | --- |  | ---

## Sheet1
Document Table Summary |  |  | Shop Drawing Table Summary
Doc Types | Total Docs | Submitted
PQ
MTS
MST
ITP
SDD
ICD
TCD
OMM
OTM
Warranty